## (IR)-Arch.
Open | 0 | #DIV/0! | 9 - Inspection Request – (IR) CONTECH Log (Architecture) | [8 empty] | Project: |  | Badya
Replied | 0 | #DIV/0! | [9 empty] | Contract: |  | 500-004-CC-P8
Overdue | 0 | #DIV/0! | [9 empty] | Contractor: |  | CON.TECH
Reply With Delay | 0 | #DIV/0! | [9 empty] | Consultant: |  | Julius Berger International
Total Actions | 0 | #DIV/0! | [9 empty] | Due Date for Submission Rev. = (0) |  |  |  | 2
Within The Allowed Duration (in overdue field) | [11 empty] | Due Date for Submission Rev.>= (1) |  |  |  | 2
Color of the overdue cell will change to yellow when it remains 1 day only for due date | [11 empty] | Dated on |  | 2025-10-09
Inspection Request No | IR Rev. | IR Latest Rev. | IR Category | Description | Location | Received Date | Due Date | Return Date | Progress | Overdue | Status | Multi Action | Ball In Court | Remarks | Soft (PDF) √ - ꓫ | FileNet | Action By
BADYA-CON-D6-A1-IR-ARCH-001 | 0 | L |  | FULL HEIGHT BIOCKWORK UNDER SOG AT A1-03-03 TRIO-CM | A1-03-03 | 2025-08-03 | 2025-08-05 |  |  |  |  | B
BADYA-CON-D6-A1-IR-ARCH-002 | 0 | L |  | FULL HEIGHT BIOCKWORK UNDER SOG AT A1-03-05 TRIO-CM | A1-03-05 | 2025-08-03 | 2025-08-05 |  |  |  |  | B
BADYA-CON-D6-A1-IR-ARCH-003 | 0 | L |  | FULL HEIGHT BIOCKWORK UNDER SOG AT A1-03-07 TRIO-C | A1-03-07 | 2025-08-03 | 2025-08-05 |  |  |  |  | B
BADYA-CON-D6-A1-IR-ARCH-004 | 0 | L |  | 1st COURSE BIOCKWORK FOR 1st FLOOR AT A1-03-07 TRIO-C | A1-03-07 | 2025-08-14 | 2025-08-19 |  |  |  |  | C
BADYA-CON-D6-A1-IR-ARCH-004 | 1 | L |  | 1st COURSE BIOCKWORK FOR 1st FLOOR AT A1-03-07 TRIO-C | A1-03-07 | 2025-08-20 | 2025-08-25 |  |  |  |  | B
BADYA-CON-D6-A1-IR-ARCH-005 | 0 | L |  | 1st COURSE FOR 1st FLOOR AT A1-03-01 TRIO-C | A1-03-01 | 2025-08-25 | 2025-08-28 |  |  |  |  | B
BADYA-CON-D6-A1-IR-ARCH-006 | 0 | L |  | FULL HEIGHT BIOCKWORK UNDER SOG AT A1-03-01 TRIO-C | A1-03-01 | 2025-08-25 | 2025-08-28 |  |  |  |  | B
BADYA-CON-D6-A1-IR-ARCH-007 | 0 | L |  | FULL HEIGHT BIOCKWORK UNDER SOG AT A1-03-02 TRIO-Cm | A1-03-02 | 2025-08-25 | 2025-08-28 |  |  |  |  | B
BADYA-CON-D6-A1-IR-ARCH-008 | 0 | L |  | 1st COURSE FOR 1st FLOOR AT A1-03-03 TRIO-CM | A1-03-03 | 2025-09-07 | 2025-09-07 |  |  |  |  | B
BADYA-CON-D6-A1-IR-ARCH-009 | 0 | L |  | 1st COURSE FOR 1st FLOOR AT A1-03-05 TRIO-CM | A1-03-05 | 2025-09-07 | 2025-09-07 |  |  |  |  | B
BADYA-CON-D6-A1-IR-ARCH-010 | 0 | L |  | 1st COURSE BLOCK WORK FOR 1ST FLOOR AT A1-03-02 TRIO-CM | A1-03-02 | 2025-09-21 | 2025-09-23 |  |  |  |  | B
BADYA-CON-D6-A1-IR-ARCH-011 | 0 | L |  | 1st First Course For 1st Floor at A1-03-06 Cor-cm | A1-03-06 | 2025-09-24 | 2025-09-25 |  |  |  |  | B
BADYA-CON-D6-A1-IR-ARCH-012 | 0 | L |  | 1st First Course For 2ND Floor at A1-03-07 trio-c | A1-03-07 | 2025-09-24 | 2025-09-25 |  |  |  |  | B
BADYA-CON-D6-A1-IR-ARCH-013 | 0 | L |  | FULL HEIGHT FOR 1ST FLOOR AT A1-03-07 TRIO-C | A1-03-07 | 2025-09-24 | 2025-09-27 |  |  |  |  | B
BADYA-CON-D6-A1-IR-ARCH-014 | 0 | L |  | 1st COURSE BLOCK WORK FOR 1ST FLOOR AT A1-03-04 COR-C | A1-03-04 | 2025-09-25 | 2025-09-27 |  |  |  |  | B
BADYA-CON-D6-A1-IR-ARCH-015 | 0 | L |  | 1st First Course For 2ND Floor Trio-cm at A1-03-02 | A1-03-02 | 2025-10-06

## (IR)-Civil-Structure
Open | 0 | 0 | 0% | 9- Inspection Request-(IR) CONTECH Log (Civil/Structure) | [6 empty] | Project: |  | Badya
Replied | 0 | 64 | 25.7% | [7 empty] | Contract: |  | 500-004-CC-P8
Overdue | 0 | 1 | 0.4016% | [7 empty] | Contractor: |  | CON.TECH
Reply With Delay | 0 | 184 | 73.9% | [7 empty] | Consultant: |  | Julius Berger International
Total Actions | 0 | 249 | 100% | [7 empty] | Due Date for Submission Rev. = (0) |  |  |  | 2
Within The Allowed Duration (in overdue field) | [10 empty] | Due Date for Submission Rev.>= (1) |  |  |  | 2
Color of the overdue cell will change to yellow when it remains 1 day only for due date | [10 empty] | Dated on |  | 2025-10-09
Inspection Request No | IR Rev. | HYPERLINK | IR Latest Rev. | IR Category | Description | Location | Received Date | Return Date | DURATION | Status | Multi Action | Ball In Court | Remarks | Soft (PDF) √- ꓫ | FileNet
BADYA-CON-D6-A1-IR-CIVIL-0001 | 0 | HYPERLINK | L | Cvil | FORM WORK FOR PC. FOOTINGS FOR (A1-03-03)&(A1-03-04) | (A1-03-03)&(A1-03-04) | 2025-03-17 | 2025-03-22 | 5 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0002 | 0 | HYPERLINK | - |  | FORM WORK FOR PC. FOOTINGS FOR (A1-03-01)&(A1-03-02) | (A1-03-01)&(A1-03-02) | 2025-03-19 | 2025-03-22 | 3 | R. with Delay | C
BADYA-CON-D6-A1-IR-CIVIL-0002 | 1 | HYPERLINK | - |  | FORM WORK FOR PC. FOOTINGS FOR (A1-03-01)&(A1-03-02) | (A1-03-01)&(A1-03-02) | 2025-04-08 | 2025-04-08 | 0 | Replied | C
BADYA-CON-D6-A1-IR-CIVIL-0002 | 2 | HYPERLINK | L |  | FORM WORK FOR PC. FOOTINGS FOR (A1-03-01)&(A1-03-02) | (A1-03-01)&(A1-03-02) | 2025-05-28 | 2025-06-01 |  | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0003 | 0 | HYPERLINK | - |  | FORM WORK AND STEEL RFT. FOT RC. FOOTINGS AND GROUND BEAMS OF (A1-03-03)&(A1-03-04) | (A1-03-03)&(A1-03-04) | 2025-03-23 | 2025-03-24 | 1 | Replied | C
BADYA-CON-D6-A1-IR-CIVIL-0003 | 1 | HYPERLINK | L |  | FORM WORK AND STEEL RFT. FOT RC. FOOTINGS AND GROUND BEAMS OF (A1-03-03)&(A1-03-04) | (A1-03-03)&(A1-03-04) | 2025-03-27 | 2025-04-06 | 10 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0004 | 0 | HYPERLINK | L |  | STEEL RFT. FOR THE GROUND FLOOR COLUMNS OF (A1-03-03),(A1-03-04) | (A1-03-03),(A1-03-04) | 2025-04-08 | 2025-04-08 | 0 | Replied | D
BADYA-CON-D6-A1-IR-CIVIL-0005 | 0 | HYPERLINK | - |  | STEEL RFT. FOR THE GROUND FLOOR COLUMNS OF (A1-03-03) | (A1-03-03) | 2025-04-09 | 2025-04-10 | 1 | Replied | C
BADYA-CON-D6-A1-IR-CIVIL-0005 | 1 | HYPERLINK | L |  | STEEL RFT. FOR THE GROUND FLOOR COLUMNS OF (A1-03-03) | (A1-03-03) | 2025-05-28 | 2025-06-01 | 4 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0006 | 0 | HYPERLINK | - |  | STEEL RFT. FOR THE GROUND FLOOR COLUMNS OF (A1-03-04) | (A1-03-04) | 2025-04-09 | 2025-04-10 | 1 | Replied | C
BADYA-CON-D6-A1-IR-CIVIL-0006 | 1 | HYPERLINK | L |  | STEEL RFT. FOR THE GROUND FLOOR COLUMNS OF (A1-03-04) | (A1-03-04) | 2025-05-28 | 2025-06-01 | 4 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0007 | 0 | HYPERLINK | - |  | FORM WORK FOR PC. FOOTINGS FOR (A1-05-01)&(A1-05-02) | (A1-05-01)&(A1-05-02) | 2025-04-28 | 2025-04-29 | 1 | Replied | C
BADYA-CON-D6-A1-IR-CIVIL-0007 | 1 | HYPERLINK | - |  | FORM WORK FOR PC. FOOTINGS FOR (A1-05-01)&(A1-05-02) | (A1-05-01)&(A1-05-02) | 2025-05-11 |  | -45788 | Overdue | C
BADYA-CON-D6-A1-IR-CIVIL-0007 | 2 | HYPERLINK | - |  | FORM WORK FOR PC. FOOTINGS FOR (A1-05-01)&(A1-05-02) | (A1-05-01)&(A1-05-02) | 2025-06-03 | 2025-06-16 | 13 | R. with Delay | C
BADYA-CON-D6-A1-IR-CIVIL-0007 | 3 | HYPERLINK | L |  | FORM WORK FOR PC. FOOTINGS FOR (A1-05-01)&(A1-05-02) | (A1-05-01)&(A1-05-02) | 2025-06-23 | 2025-07-01 | 8 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0008 | 0 | HYPERLINK | - |  | FORM WORK FOR PC. FOOTINGS FOR (A1-06-01)&(A1-06-02) | (A1-06-01)&(A1-06-02) | 2025-05-24 | 2025-05-26 | 2 | Replied | C
BADYA-CON-D6-A1-IR-CIVIL-0008 | 1 | HYPERLINK | L |  | FORM WORK FOR PC. FOOTINGS FOR (A1-06-01)&(A1-06-02) | (A1-06-01)&(A1-06-02) | 2025-06-24 | 2025-07-01 | 7 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0009 | 0 | HYPERLINK | - |  | FORM WORK FOR PC. FOOTINGS FOR (A1-05-06)&(A1-05-07) | (A1-05-06)&(A1-05-07) | 2025-05-25 | 2025-05-26 | 1 | Replied | C
BADYA-CON-D6-A1-IR-CIVIL-0009 | 1 | HYPERLINK | L |  | FORM WORK FOR PC. FOOTINGS FOR (A1-05-06)&(A1-05-07) | (A1-05-06)&(A1-05-07) | 2025-05-28 | 2025-06-01 | 4 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0010 | 0 | HYPERLINK | L |  | FORM WORK FOR THE GROUND FLOOR COLUMNS OF (A1-03-04) | (A1-03-04) | 2025-05-31 | 2025-06-16 | 16 | R. with Delay | B | kamal
BADYA-CON-D6-A1-IR-CIVIL-0011 | 0 | HYPERLINK | L |  | FORM WORK FOR THE GROUND FLOOR COLUMNS OF (A1-03-03) | (A1-03-03) | 2025-05-31 | 2025-06-16 | 16 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0012 | 0 | HYPERLINK | L |  | FORM WORK AND STEEL RFT. FOT RC. FOOTINGS AND GROUND BEAMS OF (A1-03-01)&(A1-03-02) | (A1-03-01)&(A1-03-02) | 2025-05-31 | 2025-06-16 | 16 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0013 | 0 | HYPERLINK | L |  | FORM WORK AND STEEL RFT. FOT RC. FOOTINGS AND GROUND BEAMS OF (A1-05-06)&(A1-05-07) | (A1-05-06)&(A1-05-07) | 2025-05-31 | 2025-06-16 | 16 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0014 | 0 | HYPERLINK | L |  | STEEL RFT. FOR THE GROUND FLOOR COLUMNS OF (A1-03-01) | (A1-03-01) | 2025-06-03 | 2025-06-04 | 1 | Replied | B
BADYA-CON-D6-A1-IR-CIVIL-0015 | 0 | HYPERLINK | L |  | STEEL RFT. FOR THE GROUND FLOOR COLUMNS OF (A1-03-02) | (A1-03-02) | 2025-06-03 | 2025-06-04 | 1 | Replied | B
BADYA-CON-D6-A1-IR-CIVIL-0016 | 0 | HYPERLINK | - |  | FORM WORK FOR PC. FOOTINGS FOR (A1-06-05)&(A1-06-06)&(A1-06-03)&(A1-06-04) | (A1-06-05)&(A1-06-06)&(A1-06-03)&(A1-06-04) | 2025-06-03 | 2025-06-04 | 1 | Replied | C
BADYA-CON-D6-A1-IR-CIVIL-0016 | 1 | HYPERLINK | L |  | FORM WORK FOR PC. FOOTINGS FOR (A1-06-05)&(A1-06-06)&(A1-06-03)&(A1-06-04) | (A1-06-05)&(A1-06-06)&(A1-06-03)&(A1-06-04) | 2025-06-22 | 2025-07-01 | 9 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0017 | 0 | HYPERLINK | L |  | FORM WORK FOR PC. FOOTINGS FOR (A1-03-05)&(A1-03-06)&(A1-03-07) | (A1-03-05)&(A1-03-06)&(A1-03-07) | 2025-06-03 | 2025-06-04 | 1 | Replied | B
BADYA-CON-D6-A1-IR-CIVIL-0018 | 0 | HYPERLINK | L |  | FORM WORK FOR THE GROUND FLOOR COLUMNS OF (A1-03-01) | A1-03-01 | 2025-06-16 | 2025-06-17 | 1 | Replied | B
BADYA-CON-D6-A1-IR-CIVIL-0019 | 0 | HYPERLINK | L |  | FORM WORK FOR THE GROUND FLOOR COLUMNS OF (A1-03-02) | A1-03-02 | 2025-06-16 | 2025-06-17 | 1 | Replied | B
BADYA-CON-D6-A1-IR-CIVIL-0020 | 0 | HYPERLINK | L |  | FORM WORK AND STEEL RFT. FOT RC. FOOTINGS AND GROUND BEAMS OF (A1-03-05)&(A1-03-06)&(A1-03-07) | (A1-03-05)&(A1-03-06)&(A1-03-07) | 2025-06-17 | 2025-06-18 | 1 | Replied | B
BADYA-CON-D6-A1-IR-CIVIL-0021 | 0 | HYPERLINK | L |  | STEEL RFT. FOR THE GROUND FLOOR COLUMNS OF (A1-03-05),(A1-03-06),(A1-03-07) | (A1-03-05),(A1-03-06),(A1-03-07) | 2025-06-19 | 2025-06-22 | 3 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0022 | 0 | HYPERLINK | L |  | STEEL RFT. FOR THE GROUND FLOOR COLUMNS OF (A1-05-06) | A1-05-06 | 2025-06-23 | 2025-06-24 | 1 | Replied | B
BADYA-CON-D6-A1-IR-CIVIL-0023 | 0 | HYPERLINK | L |  | FORM WORK FOR THE GROUND FLOOR COLUMNS OF (A1-03-05),(A1-03-06),(A1-03-07) | (A1-03-05),(A1-03-06),(A1-03-07) | 2025-06-21 | 2025-06-23 | 2 | Replied | B | kamal
BADYA-CON-D6-A1-IR-CIVIL-0024 | 0 | HYPERLINK | L |  | FORM WORK FOR THE GROUND SLAB OF (A1-03-01) | A1-03-01 | 2025-06-21 | 2025-06-23 | 2 | Replied | B | kamal
BADYA-CON-D6-A1-IR-CIVIL-0025 | 0 | HYPERLINK | L |  | FORM WORK FOR THE GROUND SLAB OF (A1-03-03) | A1-03-03 | 2025-06-23 | 2025-06-27 | 4 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0026 | 0 | HYPERLINK | L |  | STEEL RFT. FOR THE GROUND FLOOR COLUMNS OF (A1-05-07) | A1-05-07 | 2025-06-23 | 2025-06-27 | 4 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0027 | 0 | HYPERLINK | L |  | FORM WORK FOR THE GROUND SLAB OF (A1-03-05) | A1-03-05 | 2025-06-23 | 2025-07-01 | 8 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0028 | 0 | HYPERLINK | L |  | FORM WORK FOR THE GROUND SLAB OF (A1-03-07) | A1-03-07 | 2025-06-23 | 2025-07-01 | 8 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0029 | 0 | HYPERLINK | L |  | STEEL RFT. FOR THE GROUND FLOOR SLAB OF (A1-03-01) | A1-03-01 | 2025-06-25 | 2025-07-01 | 6 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0030 | 0 | HYPERLINK | L |  | FORM WORK FOR THE GROUND SLAB OF (A1-03-02) | A1-03-02 | 2025-06-25 | 2025-07-01 | 6 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0031 | 0 | HYPERLINK | L |  | STEEL RFT. FOR THE GROUND FLOOR SLAB OF (A1-03-03) | A1-03-03 | 2025-06-25 | 2025-07-01 | 6 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0032 | 0 | HYPERLINK | L |  | STEEL RFT. FOR THE GROUND SLAB OF (A1-03-03) | A1-03-03 | 2025-06-28 | 2025-07-01 | 3 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0033 | 0 | HYPERLINK | L |  | FORM WORK FOR THE GROUND FLOOR COLUMNS OF (A1-05-07) | A1-05-07 | 2025-06-28 | 2025-07-01 | 3 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0034 | 0 | HYPERLINK | L |  | FORM WORK FOR THE GROUND FLOOR COLUMNS OF (A1-05-06) | A1-05-06 | 2025-06-28 | 2025-07-01 | 3 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0035 | 0 | HYPERLINK | L |  | STEEL RFT. FOR THE 1st COLUMNS OF (A1-03-03) | A1-03-03 | 2025-06-29 | 2025-07-01 | 2 | Replied | B
BADYA-CON-D6-A1-IR-CIVIL-0036 | 0 | HYPERLINK | L |  | STEEL RFT. FOR THE GR SLAB OF (A1-03-05) | A1-03-05 | 2025-07-01 | 2025-07-02 | 1 | Replied | B
BADYA-CON-D6-A1-IR-CIVIL-0037 | 0 | HYPERLINK | L |  | STEEL RFT. FOR THE GR SLAB OF (A1-03-02) | A1-03-02 | 2025-07-01 | 2025-07-02 | 1 | Replied | B
BADYA-CON-D6-A1-IR-CIVIL-0038 | 0 | HYPERLINK | L |  | FORM WORK FOR THE GROUND FLOOR SLAB OF (A1-03-04) | A1-03-04 | 2025-07-01 | 2025-07-02 | 1 | Replied | B
BADYA-CON-D6-A1-IR-CIVIL-0039 | 0 | HYPERLINK | L |  | FORM WORK FOR THE GROUND FLOOR SLAB OF (A1-03-06) | A1-03-06 | 2025-07-01 | 2025-07-02 | 1 | Replied | B
BADYA-CON-D6-A1-IR-CIVIL-0040 | 0 | HYPERLINK | L |  | STEEL RFT. FOR THE GR SLAB OF (A1-03-07) | A1-03-06 | 2025-07-01 | 2025-07-02 | 1 | Replied | B
BADYA-CON-D6-A1-IR-CIVIL-0041 | 0 | HYPERLINK | L |  | FORM WORK AND STEEL RFT. FOT RC. FOOTINGS AT (A1-05-01)&(A1-05-02) | (A1-05-01)&(A1-05-02) | 2025-07-01 | 2025-07-02 | 1 | Replied | B
BADYA-CON-D6-A1-IR-CIVIL-0042 | 0 | HYPERLINK | - |  | STEEL RFT. FOR 2ND SLAB OF (A1-03-01) | A1-03-01 | 2025-09-14 | 9/16/2025 |  |  | C
BADYA-CON-D6-A1-IR-CIVIL-0042 |  | HYPERLINK | L |  | STEEL RFT. FOR 2ND SLAB OF (A1-03-01) | A1-03-01 | 2025-09-17 | 9/24/2025 |  |  | B
BADYA-CON-D6-A1-IR-CIVIL-0043 | 0 | HYPERLINK | L |  | FORM WORK AND STEEL RFT. FOT RC. FOOTINGS AT (A1-06-01)&(A1-06-02) | (A1-06-01)&(A1-06-02) | 2025-07-06 | 2025-07-08 | 2 | Replied | B
BADYA-CON-D6-A1-IR-CIVIL-0044 | 0 | HYPERLINK | L |  | STEEL RFT. FOR THE GR SLAB OF (A1-03-04) | A1-03-04 | 2025-07-06 | 2025-07-08 | 2 | Replied | B
BADYA-CON-D6-A1-IR-CIVIL-0045 | 0 | HYPERLINK | L |  | STEEL RFT. FOR THE GR SLAB OF (A1-03-06) | A1-03-06 | 2025-07-06 | 2025-07-08 | 2 | Replied | B
BADYA-CON-D6-A1-IR-CIVIL-0046 | 0 | HYPERLINK | L |  | STEEL RFT. FOR THE GR COLUMNS OF (A1-05-02) | A1-05-02 | 2025-07-06 | 2025-07-08 | 2 | Replied | B
BADYA-CON-D6-A1-IR-CIVIL-0047 | 0 | HYPERLINK | L |  | STEEL RFT. FOR THE 1st COLUMNS OF (A1-03-01) | A1-03-01 | 2025-07-08 | 2025-07-09 | 1 | Replied | B
BADYA-CON-D6-A1-IR-CIVIL-0048 | 0 | HYPERLINK | L |  | STEEL RFT. FOR THE 1st COLUMNS OF (A1-03-02) | A1-03-02 | 2025-07-08 | 2025-07-13 | 6 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0049 | 0 | HYPERLINK | L |  | STEEL RFT. FOR THE GR SLAB OF (A1-03-04) | A1-03-04 | 2025-07-08 | 2025-07-09 | 1 | Replied | D | متكرر
BADYA-CON-D6-A1-IR-CIVIL-0050 | 0 | HYPERLINK | L |  | STEEL RFT. FOR THE 1st COLUMNS OF (A1-03-05) | A1-03-05 | 2025-07-08 | 2025-07-09 | 1 | Replied | B
BADYA-CON-D6-A1-IR-CIVIL-0051 | 0 | HYPERLINK | L |  | STEEL RFT. FOR THE GR slab OF (A1-03-06) | A1-03-06 | 2025-07-08 | 2025-07-09 | 1 | Replied | D | متكرر
BADYA-CON-D6-A1-IR-CIVIL-0052 | 0 | HYPERLINK | L |  | STEEL RFT. FOR THE 1st COLUMNS OF (A1-03-07) | A1-03-07 | 2025-07-08 | 2025-07-09 | 1 | Replied | B
BADYA-CON-D6-A1-IR-CIVIL-0053 | 0 | HYPERLINK | L |  | STEEL RFT. FOR THE GR COLUMNS OF (A1-05-01) | A1-05-01 | 2025-07-08 | 2025-07-09 | 1 | Replied | B
BADYA-CON-D6-A1-IR-CIVIL-0054 | 0 | HYPERLINK | L |  | STEEL RFT. FOR THE GR COLUMNS OF (A1-05-02) | A1-05-02 | 2025-07-08 | 2025-07-13 | 5 | R. with Delay | D | متكرر
BADYA-CON-D6-A1-IR-CIVIL-0055 | 0 | HYPERLINK | L |  | FORM WORK FOR THE 1ST COLUMNS SLAB OF (A1-03-03) | A1-03-03 | 2025-07-08 | 2025-07-13 | 5 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0056 | 0 | HYPERLINK | L |  | STEEL RFT. FOR THE 1ST COLUMNS OF (A1-03-06) | A1-03-06 | 2025-07-08 | 2025-07-13 | 5 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0057 | 0 | HYPERLINK | L |  | FORM WORK FOR THE GR COLUMNS SLAB OF (A1-05-02) | A1-05-02 | 2025-07-08 | 2025-07-13 | 5 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0058 | 0 | HYPERLINK | L |  | Surface Preparation Before Insulation For RC. Foundation A (A1-03-03). | A1-03-03 | 2025-07-13 | 2025-07-15 | 2 | Replied | B
BADYA-CON-D6-A1-IR-CIVIL-0059 | 0 | HYPERLINK | L |  | Surface Preparation Before Insulation For RC. Foundation A (A1-03-07). | A1-03-07 | 2025-07-13 | 2025-07-15 | 2 | Replied | B
BADYA-CON-D6-A1-IR-CIVIL-0060 | 0 | HYPERLINK | L |  | Surface Preparation Before Insulation For RC. Foundation A (A1-03-05). | A1-03-05 | 2025-07-13 | 2025-07-15 | 2 | Replied | B
BADYA-CON-D6-A1-IR-CIVIL-0061 | 0 | HYPERLINK | L |  | FORM WORK FOR THE 1ST COLUMNS OF (A1-03-01) | A1-03-01 | 2025-07-13 | 2025-07-15 | 2 | Replied | B
BADYA-CON-D6-A1-IR-CIVIL-0062 | 0 | HYPERLINK | L |  | FORM WORK FOR THE 1ST COLUMNS OF (A1-03-05) | A1-03-05 | 2025-07-13 | 2025-07-15 | 2 | Replied | B
BADYA-CON-D6-A1-IR-CIVIL-0063 | 0 | HYPERLINK | L |  | FORM WORK FOR THE 1ST COLUMNS OF (A1-03-07) | A1-03-07 | 2025-07-13 | 2025-07-15 | 2 | Replied | B
BADYA-CON-D6-A1-IR-CIVIL-0064 | 0 | HYPERLINK | L |  | FORM WORK FOR THE GR COLUMNS OF (A1-05-01) | A1-05-01 | 2025-07-15 | 2025-07-20 | 5 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0065 | 0 | HYPERLINK | L |  | FORM WORK FOR THE 1ST SLAB OF (A1-03-03) | A1-03-03 | 2025-07-15 | 2025-07-16 | 1 | Replied | B
BADYA-CON-D6-A1-IR-CIVIL-0066 | 0 | HYPERLINK | L |  | STEEL RFT. FOR THE 1ST COLUMNS OF (A1-03-04) | A1-03-04 | 2025-07-15 | 2025-07-16 | 1 | Replied | B
BADYA-CON-D6-A1-IR-CIVIL-0067 | 0 | HYPERLINK | L |  | FORM WORK FOR THE 1ST COLUMNS OF (A1-03-06) | A1-03-06 | 2025-07-15 | 2025-07-16 | 1 | Replied | B
BADYA-CON-D6-A1-IR-CIVIL-0068 | 0 | HYPERLINK | L |  | FORM WORK FOR THE 1ST COLUMNS OF (A1-03-02) | A1-03-02 | 2025-07-15 | 2025-07-20 | 5 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0069 | 0 | HYPERLINK | L |  | FORM WORK AND STEEL RFT. FOT RC. FOOTINGS AT (A1-06-03)&(A1-06-04)&(A1-06-05)&(A1-06-06) | (A1-06-03)&(A1-06-04)&(A1-06-05)&(A1-06-06) | 2025-07-15 | 2025-07-16 | 1 | Replied | B
BADYA-CON-D6-A1-IR-CIVIL-0070 | 0 | HYPERLINK | L |  | FORM WORK FOR THE 1ST SLAB OF (A1-03-05) | A1-03-05 | 2025-07-16 | 2025-07-20 | 4 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0071 | 0 | HYPERLINK | L |  | FORM WORK FOR THE gr SLAB OF (A1-05-06) | A1-05-06 | 2025-07-16 | 2025-07-20 | 4 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0072 | 0 | HYPERLINK | L |  | FORM WORK FOR PC. FOOTINGS FOR (A1-05-03)&(A1-05-04)&(A1-05-05) | (A1-05-03)&(A1-05-04)&(A1-05-05) | 2025-07-16 | 2025-07-20 | 4 | R. with Delay | A
BADYA-CON-D6-A1-IR-CIVIL-0073 | 0 | HYPERLINK | L |  | FORM WORK FOR THE GR SLAB OF (A1-05-07) | A1-05-07 | 2025-07-17 | 2025-07-20 | 3 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0074 | 0 | HYPERLINK | L |  | STEEL RFT. FOR THE GR COLUMNS OF (A1-06-03) | A1-06-03 | 2025-07-17 | 2025-07-20 | 3 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0075 | 0 | HYPERLINK | L |  | STEEL RFT. FOR THE GR COLUMNS OF (A1-06-04) | A1-06-04 | 2025-07-17 | 2025-07-20 | 3 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0076 | 0 | HYPERLINK | L |  | STEEL RFT. FOR THE GR COLUMNS OF (A1-06-06) | A1-06-06 | 2025-07-17 | 2025-07-20 | 3 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0077 | 0 | HYPERLINK | L |  | 1ST COAT OF INSULATION FOR RC Foundation AT (A1-03-01). | A1-03-01 | 2025-07-21 | 2025-07-24 | 3 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0078 | 0 | HYPERLINK | L |  | Surface Preparation Before Insulation For RC. Foundation AT (A1-03-01). | A1-03-01 | 2025-07-17 | 2025-07-20 | 3 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0079 | 0 | HYPERLINK | L |  | 1ST COAT OF INSULATION FOR RC Foundation AT (A1-03-07). | A1-03-07 | 2025-07-17 | 2025-07-20 | 3 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0080 | 0 | HYPERLINK | L |  | 1ST COAT OF INSULATION FOR RC Foundation AT (A1-03-05). | A1-03-05 | 2025-07-17 | 2025-07-20 | 3 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0081 | 0 | HYPERLINK | L |  | 1ST COAT OF INSULATION FOR RC Foundation AT (A1-03-03). | A1-03-03 | 2025-07-17 | 2025-07-20 | 3 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0082 | 0 | HYPERLINK | L |  | FORM WORK FOR THE 1ST COLUMNS OF (A1-03-04) | A1-03-04 | 2025-07-21 | 2025-07-24 | 3 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0083 | 0 | HYPERLINK | L |  | FORM WORK FOR THE 1ST SLAB OF (A1-03-01) | A1-03-01 | 2025-07-21 | 2025-07-24 | 3 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0084 | 0 | HYPERLINK | L |  | FORM WORK FOR THE 1ST SLAB OF (A1-03-07) | A1-03-07 | 2025-07-21 | 2025-07-24 | 3 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0085 | 0 | HYPERLINK | L |  | STEEL RFT. FOR THE GR SLAB OF (A1-03-03) | A1-03-03 | 2025-07-21 | 2025-07-24 | 3 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0086 | 0 | HYPERLINK | L |  | 2nd COAT OF INSULATION FOR RC Foundation AT (A1-03-07). | A1-03-07 | 2025-07-21 | 2025-07-24 | 3 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0087 | 0 | HYPERLINK | L |  | 2nd COAT OF INSULATION FOR RC Foundation AT (A1-03-05). | A1-03-05 | 2025-07-21 | 2025-07-24 | 3 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0088 | 0 | HYPERLINK | L |  | 2nd COAT OF INSULATION FOR RC Foundation AT (A1-03-03). | A1-03-03 | 2025-07-21 | 2025-07-24 | 3 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0089 | 0 | HYPERLINK | L |  | STEEL RFT. FOR THE 1st SLAB OF (A1-03-05) | A1-03-05 | 2025-07-21 | 2025-07-28 | 7 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0090 | 0 | HYPERLINK | L |  | STEEL RFT. FOR THE GR COLUMNS OF (A1-06-02) | A1-06-02 | 2025-07-22 | 2025-07-28 | 6 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0091 | 0 | HYPERLINK | L |  | FORM WORK AND STEEL RFT. FOT RC. FOOTINGS AT (A1-05-03) | A1-05-03 | 2025-07-22 | 2025-08-04 | 13 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0092 | 0 | HYPERLINK | L |  | FORM WORK FOR THE GR SLAB OF (A1-06-06) | A1-06-06 | 2025-07-22 | 2025-07-28 | 6 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0093 | 0 | HYPERLINK | L |  | Surface Preparation Before Insulation For RC. Foundation AT (A1-03-06). | A1-03-06 | 2025-07-22 | 2025-07-28 | 6 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0094 | 0 | HYPERLINK | L |  | FORM WORK FOR THE 1st SLAB OF (A1-03-02) | A1-03-02 | 2025-07-23 | 2025-07-28 | 5 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0095 | 0 | HYPERLINK | L |  | FORM WORK FOR THE GR COLUMNS OF (A1-06-03) | A1-03-03 | 2025-07-23 | 2025-07-28 | 5 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0096 | 0 | HYPERLINK | L |  | FORM WORK FOR THE GR COLUMNS OF (A1-06-04) | A1-03-04 | 2025-07-23 | 2025-07-28 | 5 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0097 | 0 | HYPERLINK | L |  | Surface Preparation Before Insulation For RC FOOTING AT (A1-03-02). | A1-03-02 | 2025-07-27 | 2025-07-30 | 3 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0098 | 0 | HYPERLINK | L |  | 2nd COAT OF INSULATION FOR RC FOOTING AT (A1-03-01). | A1-03-01 | 2025-07-27 | 2025-07-30 | 3 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0099 | 0 | HYPERLINK | L |  | 1ST COAT OF INSULATION FOR RC FOOTING AT (A1-03-06). | A1-03-06 | 2025-07-27 | 2025-07-30 | 3 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0100 | 0 | HYPERLINK | L |  | STEEL RFT. FOR THE 2ND COULMNS OF (A1-03-03) | A1-03-03 | 2025-07-27 | 2025-07-30 | 3 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0101 | 0 | HYPERLINK | L |  | FORM WORK FOR GROUND COLUMNS OF (A1-06-02) | A1-06-02 | 2025-07-27 | 2025-07-30 | 3 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0102 | 0 | HYPERLINK | L |  | STEEL RFT. FOR GROUND COLUMNS OF (A1-06-05) | A1-06-05 | 2025-07-27 | 2025-07-30 | 3 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0103 | 0 | HYPERLINK | L |  | STEEL RFT. FOR GROUND SLAB OF (A1-05-06) | A1-05-06 | 2025-07-27 | 2025-07-30 | 3 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0104 | 0 | HYPERLINK | L |  | Surface Preparation to close NCR-STR-NO.1(A1-05-03) | A1-05-03 | 2025-07-28 | 2025-08-02 | 5 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0105 | 0 | HYPERLINK | L |  | STEEL RFT. FOR THE 1st SLAB OF (A1-03-01) | A1-03-01 | 2025-07-28 | 2025-07-30 | 2 | Replied | B
BADYA-CON-D6-A1-IR-CIVIL-0106 | 0 | HYPERLINK | L |  | STEEL RFT. FOR THE 1st SLAB OF (A1-03-07) | A1-03-07 | 2025-07-28 | 2025-07-30 | 2 | Replied | B
BADYA-CON-D6-A1-IR-CIVIL-0107 | 0 | HYPERLINK | L |  | 3rd COAT OF INSULATION FOR RC FOOTING AT (A1-03-07). | A1-03-07 | 2025-07-28 | 2025-07-30 | 2 | Replied | B
BADYA-CON-D6-A1-IR-CIVIL-0108 | 0 | HYPERLINK | L |  | 3rd COAT OF INSULATION FOR RC FOOTING AT (A1-03-05). | A1-03-05 | 2025-07-28 | 2025-07-30 | 2 | Replied | B
BADYA-CON-D6-A1-IR-CIVIL-0109 | 0 | HYPERLINK | L |  | 3rd COAT OF INSULATION FOR RC FOOTING AT (A1-03-03). | A1-03-03 | 2025-07-28 | 2025-07-30 | 2 | Replied | B
BADYA-CON-D6-A1-IR-CIVIL-0110 | 0 | HYPERLINK | L |  | FORM WORK FOR 1st SLAB OF (A1-03-06) | A1-03-06 | 2025-07-28 | 2025-07-30 | 2 | Replied | B
BADYA-CON-D6-A1-IR-CIVIL-0111 | 0 | HYPERLINK | L |  | FORM WORK FOR 1st SLAB OF (A1-03-04) | A1-03-04 | 2025-07-29 | 2025-08-04 | 6 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0112 | 0 | HYPERLINK | L |  | FORM WORK FOR 2nd SLAB OF (A1-03-02) | (A1-03-02 | 2025-08-31 | 2025-09-02 | 2 | Replied | B
BADYA-CON-D6-A1-IR-CIVIL-0113 | 0 | HYPERLINK | L |  | FORM WORK FOR 2nd SLAB OF (A1-03-04) | (A1-03-04 | 2025-08-31 | 2025-09-02 | 2 | Replied | B
BADYA-CON-D6-A1-IR-CIVIL-0114 | 0 | HYPERLINK | L |  | STEEL RFT. FOR 1ST SLAB OF (A1-03-02) | A1-03-02 | 2025-07-30 | 2025-08-04 | 5 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0115 | 0 | HYPERLINK | L |  | STEEL RFT. FOR GR COLUMNS OF (A1-05-07) | A1-05-07 | 2025-07-30 | 2025-08-04 | 5 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0116 | 0 | HYPERLINK | L |  | STEEL RFT. FOR GR COLUMNS OF (A1-06-01) | A1-06-01 | 2025-07-30 | 2025-08-04 | 5 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0117 | 0 | HYPERLINK | L |  | FINAL RAPICRR TO CLOSE NCR STR NO.1 AT (A1-05-03) | A1-05-03 | 2025-07-30 | 2025-08-02 | 3 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0118 | 0 | HYPERLINK | L |  | STEEL RFT. FOR 2nd COLUMNS OF (A1-03-02) | A1-03-02 | 2025-07-31 | 2025-08-04 | 4 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0119 | 0 | HYPERLINK | L |  | STEEL RFT. FOR 1st SLAB OF (A1-03-06) | A1-03-06 | 2025-07-31 | 2025-08-04 | 4 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0120 | 0 | HYPERLINK | L |  | FORM WORK FOR GR COLUMNS OF (A1-06-05) | A1-06-05 | 2025-07-31 | 2025-08-04 | 4 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0121 | 0 | HYPERLINK | L |  | 1ST COAT OF INSULATION FOR RC FOOTING AT (A1-03-02). | A1-03-02 | 2025-07-31 | 2025-08-04 | 4 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0122 | 0 | HYPERLINK | L |  | 2ND COAT OF INSULATION FOR RC FOOTING AT (A1-03-06). | A1-03-06 | 2025-07-31 | 2025-08-04 | 4 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0123 | 0 | HYPERLINK | L |  | 3RD COAT OF INSULATION FOR RC FOOTING AT (A1-03-01). | A1-03-01 | 2025-07-31 | 2025-08-04 | 4 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0124 | 0 | HYPERLINK | L |  | FORM WORK FOR 2nd COLUMNS OF (A1-03-03) | A1-03-03 | 2025-08-03 | 2025-08-06 | 3 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0125 | 0 | HYPERLINK | L |  | STEEL RFT. FOR 2nd COLUMNS OF (A1-03-05) | A1-03-05 | 2025-08-03 | 2025-08-06 | 3 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0126 | 0 | HYPERLINK | L |  | STEEL RFT. FOR 2nd COLUMNS OF (A1-03-01) | A1-03-01 | 2025-08-03 | 2025-08-06 | 3 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0127 | 0 | HYPERLINK | L |  | STEEL RFT. FOR 2nd COLUMNS OF (A1-03-07) | A1-03-07 | 2025-08-03 | 2025-08-06 | 3 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0128 | 0 | HYPERLINK | L |  | Surface Preparation Before Insulation For RC FOOTING AT (A1-03-04). | A1-03-04 | 2025-08-04 | 2025-08-10 | 6 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0129 | 0 | HYPERLINK | L |  | FORM WORK AND STEEL RFT. FOT RC. FOOTINGS AT (A1-05-04) | A1-05-04 | 2025-08-04 | 2025-08-10 | 6 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0130 | 0 | HYPERLINK | L |  | FORM WORK FOR GR SLAB OF (A1-06-06) | A1-06-06 | 2025-08-04 | 2025-08-10 | 6 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0131 | 0 | HYPERLINK | L |  | 2ND COAT OF INSULATION FOR RC FOOTING AT (A1-03-02). | A1-03-02 | 2025-08-05 | 2025-08-10 | 5 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0132 | 0 | HYPERLINK | L |  | 3RD COAT OF INSULATION FOR RC FOOTING AT (A1-03-06). | A1-03-06 | 2025-08-05 | 2025-08-10 | 5 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0133 | 0 | HYPERLINK | L |  | STEEL RFT. FOR 1ST SLAB OF (A1-03-04) | A1-03-04 | 2025-08-05 | 2025-08-10 | 5 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0134 | 0 | HYPERLINK | L |  | STEEL RFT. FOR GR COLUMNS OF (A1-05-03) | A1-05-03 | 2025-08-05 | 2025-08-10 | 5 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0135 | 0 | HYPERLINK | L |  | FORM WORK FOR GR SLAB OF (A1-05-01) | A1-05-01 | 2025-08-05 | 2025-08-10 | 5 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0136 | 0 | HYPERLINK | L |  | FORM WORK FOR GR COLUMNS OF (A1-06-01) | A1-06-01 | 2025-08-05 | 2025-08-10 | 5 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0137 | 0 | HYPERLINK | L |  | FORM WORK FOR GR SLAB OF (A1-06-03) | A1-06-03 | 2025-08-05 | 2025-08-10 | 5 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0138 | 0 | HYPERLINK | L |  | FORM WORK FOR GR SLAB OF (A1-06-02) | A1-06-02 | 2025-08-06 | 2025-08-10 | 4 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0139 | 0 | HYPERLINK | L |  | FORM WORK FOR 2D COLUMNS OF (A1-03-05) | A1-03-05 | 2025-08-06 | 2025-08-10 | 4 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0140 | 0 | HYPERLINK | L |  | FORM WORK FOR 2D COLUMNS OF (A1-03-07) | A1-03-07 | 2025-08-06 | 2025-08-10 | 4 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0141 | 0 | HYPERLINK | L |  | FORM WORK FOR 2D COLUMNS OF (A1-03-01) | A1-03-01 | 2025-08-06 | 2025-08-10 | 4 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0142 | 0 | HYPERLINK | L |  | FORM WORK FOR 2D COLUMNS OF (A1-03-02) | A1-03-02 | 2025-08-06 | 2025-08-20 | 14 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0143 | 0 | HYPERLINK | L |  | Surface Preparation to close NCR-STR-NO.3 at (A1-06-02) | A1-06-02 | 2025-08-07 | 2025-08-10 | 3 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0144 | 0 | HYPERLINK | L |  | STEEL RFT. FOR 1ST COLUMNS OF (A1-05-06) | A1-05-06 | 2025-08-11 | 2025-08-17 | 6 | R. with Delay | B | K
BADYA-CON-D6-A1-IR-CIVIL-0145 | 0 | HYPERLINK | L |  | FORM WORK FOR GR SLAB OF (A1-06-04) | A1-06-04 | 2025-08-11 | 2025-08-17 | 6 | R. with Delay | B | K
BADYA-CON-D6-A1-IR-CIVIL-0146 | 0 | HYPERLINK | L |  | 3RD COAT OF INSULATION FOR RC FOOTING AT (A1-03-02). | A1-03-02 | 2025-08-11 | 2025-08-17 | 6 | R. with Delay | B | K
BADYA-CON-D6-A1-IR-CIVIL-0147 | 0 | HYPERLINK | L |  | 1ST COAT OF INSULATION FOR RC FOOTING AT (A1-03-04). | A1-03-04 | 2025-08-11 | 2025-08-17 | 6 | R. with Delay | B | K
BADYA-CON-D6-A1-IR-CIVIL-0148 | 0 | HYPERLINK | L |  | STEEL RFT. FOR 2ND COLUMNS OF (A1-03-06) | A1-03-06 | 2025-08-11 | 2025-08-17 | 6 | R. with Delay | B | K
BADYA-CON-D6-A1-IR-CIVIL-0149 | 0 | HYPERLINK | L |  | STEEL RFT. FOR 2ND COLUMNS OF (A1-03-04) | A1-03-04 | 2025-08-11 | 2025-08-20 | 9 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0150 | 0 | HYPERLINK | L |  | STEEL RFT. FOR GR SLAB OF (A1-06-06) | A1-06-06 | 2025-08-11 | 2025-08-17 | 6 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0151 | 0 | HYPERLINK | L |  | STEEL RFT. FOR GR SLAB OF (A1-06-02) | A1-06-02 | 2025-08-11 | 2025-08-17 | 6 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0152 | 0 | HYPERLINK | L |  | STEEL RFT. FOR GR SLAB OF (A1-06-03) | A1-06-03 | 2025-08-11 | 2025-08-17 | 6 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0153 | 0 | HYPERLINK | L |  | FORM WORK FOR GR COLUMNS OF (A1-05-03) | A1-05-03 | 2025-08-11 | 2025-08-20 | 9 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0154 | 0 | HYPERLINK | L |  | 1ST COAT OF INSULATION FOR UNDER SOG AT (A1-03-07). | A1-03-07 | 2025-08-11 | 2025-08-17 | 6 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0155 | 0 | HYPERLINK | L |  | 1ST COAT OF INSULATION FOR UNDER SOG AT (A1-03-05). | A1-03-05 | 2025-08-11 | 2025-08-17 | 6 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0156 | 0 | HYPERLINK | L |  | 1ST COAT OF INSULATION FOR UNDER SOG AT (A1-03-03). | A1-03-03 | 2025-08-11 | 2025-08-17 | 6 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0157 | 0 | HYPERLINK | L |  | FINAL REPAIR to close NCR-STR-NO.3 at (A1-06-02) | A1-06-02 | 2025-08-12 | 2025-08-25 | 13 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0158 | 0 | HYPERLINK | L |  | FORM WORK FOR GR SLAB AT (A1-05-02) | A1-05-02 | 2025-08-14 | 2025-08-25 | 11 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0159 | 0 | HYPERLINK | L |  | STEEL RFT. FOR 1ST COLUMNS OF (A1-05-07) | A1-05-07 | 2025-08-14 | 2025-08-20 | 6 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0160 | 0 | HYPERLINK | L |  | FORM WORK FOR 2ND SLAB AT (A1-03-07) | A1-03-07 | 2025-08-14 | 2025-08-25 | 11 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0161 | 0 | HYPERLINK | - |  | FORM WORK FOR 2ND SLAB AT (A1-03-01) | A1-03-01 | 2025-08-14 | 2025-08-24 | 10 | R. with Delay | C
BADYA-CON-D6-A1-IR-CIVIL-0161 | 1 | HYPERLINK | L |  | FORM WORK FOR 2ND SLAB AT (A1-03-01) | A1-03-01 | 2025-08-31 | 2025-09-11 | 11 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0162 | 0 | HYPERLINK | L |  | FORM WORK FOR GR SLAB AT (A1-06-05) | A1-06-05 | 2025-08-14 | 2025-08-25 | 11 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0163 | 0 | HYPERLINK | L |  | STEEL RFT. FOR GR SLAB AT (A1-05-01) | A1-05-01 | 2025-08-17 | 2025-08-20 | 3 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0164 | 0 | HYPERLINK | - |  | STEEL RFT. FOR GR COLUMNS AT (A1-05-04) | A1-05-04 | 2025-08-17 | 2025-08-20 | 3 | R. with Delay | C
BADYA-CON-D6-A1-IR-CIVIL-0164 | 1 | HYPERLINK | L |  | STEEL RFT. FOR GR COLUMNS AT (A1-05-04) | A1-05-04 | 2025-09-06 | 2025-09-09 | 3 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0165 | 0 | HYPERLINK | L |  | FORM WORK FOR GR SLAB AT (A1-06-01) | A1-06-01 | 2025-08-20 | 2025-08-25 | 5 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0166 | 0 | HYPERLINK | L |  | 2ND COAT OF INSULATION FOR UNDER SOG AT (A1-03-03). | A1-03-03 | 2025-08-17 | 2025-08-20 | 3 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0167 | 0 | HYPERLINK | L |  | 2ND COAT OF INSULATION FOR UNDER SOG AT (A1-03-05). | A1-03-05 | 2025-08-17 | 2025-08-20 | 3 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0168 | 0 | HYPERLINK | L |  | 2ND COAT OF INSULATION FOR UNDER SOG AT (A1-03-07). | A1-03-07 | 2025-08-17 | 2025-08-20 | 3 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0169 | 0 | HYPERLINK | L |  | FORM WORK FOR 2ND COLUMNS AT (A1-03-06) | A1-03-06 | 2025-08-17 | 2025-08-20 | 3 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0170 | 0 | HYPERLINK | L |  | FORM WORK FOR 2ND SLAB AT (A1-03-05) | A1-03-05 | 2025-08-17 | 2025-08-20 | 3 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0171 | 0 | HYPERLINK | L |  | FORM WORK FOR 1ST COLUMNS AT (A1-05-06) | A1-05-06 | 2025-08-17 | 2025-08-20 | 3 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0172 | 0 | HYPERLINK | L |  | STEEL RFT. FOR GR SLAB AT (A1-06-04) | A1-06-04 | 2025-08-17 | 2025-08-25 | 8 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0173 | 0 | HYPERLINK | L |  | FORM WORK AND STEEL RFT FOR RC FOOTING AT (A1-05-05) | A1-05-05 | 2025-08-20 | 2025-08-25 | 5 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0174 | 0 | HYPERLINK | L |  | STEEL RFT FOR 1ST AT COLUMNS (A1-06-06) | A1-06-06 | 2025-08-20 | 2025-08-25 | 5 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0175 | 0 | HYPERLINK | L |  | FORM WORK FOR 1ST COLUMNS AT (A1-05-07) | A1-06-07 | 2025-08-20 | 2025-08-25 | 5 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0176 | 0 | HYPERLINK | L |  | FORM WORK FOR GR SLAB AT (A1-05-03) | A1-05-03 | 2025-08-20 | 2025-08-25 | 5 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0177 | 0 | HYPERLINK | L |  | FORM WORK FOR 2ND SLAB AT (A1-03-03) | A1-03-03 | 2025-08-20 | 2025-08-25 | 5 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0178 | 0 | HYPERLINK | L |  | FORM WORK FOR 2ND COLUMNS AT (A1-03-04) | A1-03-04 | 2025-08-20 | 2025-08-25 | 5 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0179 | 0 | HYPERLINK | L |  | STEEL RFT. FOR 1ST COLUMNS OF (A1-06-03) | A1-06-03 | 2025-08-20 | 2025-08-25 | 5 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0180 | 0 | HYPERLINK | L |  | 3RD COAT OF INSULATION FOR UNDER SOG AT (A1-03-03). | A1-03-03 | 2025-08-21 | 2025-08-25 | 4 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0181 | 0 | HYPERLINK | L |  | 3RD COAT OF INSULATION FOR UNDER SOG AT (A1-03-05). | A1-03-05 | 2025-08-21 | 2025-08-25 | 4 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0182 | 0 | HYPERLINK | L |  | 3RD COAT OF INSULATION FOR UNDER SOG AT (A1-03-07). | A1-03-07 | 2025-08-21 | 2025-08-25 | 4 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0183 | 0 | HYPERLINK | L |  | STEEL RFT. FOR 1ST COLUMNS OF (A1-06-02) | A1-06-02 | 2025-08-21 | 2025-08-25 | 4 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0184 | 0 | HYPERLINK | L |  | STEEL RFT. FOR 2ND SLAB AT (A1-03-03) | A1-03-03 | 2025-08-25 | 2025-09-02 | 8 | R. with Delay | B | K
BADYA-CON-D6-A1-IR-CIVIL-0185 | 0 | HYPERLINK | L |  | STEEL RFT. FOR 2ND SLAB AT (A1-03-07) | A1-03-07 | 2025-08-25 | 2025-09-02 | 8 | R. with Delay | B | K
BADYA-CON-D6-A1-IR-CIVIL-0186 | 0 | HYPERLINK | L |  | STEEL RFT. FOR GR SLAB AT (A1-05-03) | A1-05-03 | 2025-08-25 | 2025-09-02 | 8 | R. with Delay | B | K
BADYA-CON-D6-A1-IR-CIVIL-0187 | 0 | HYPERLINK | L |  | STEEL RFT. FOR GR SLAB AT (A1-05-02) | A1-05-02 | 2025-08-25 | 2025-09-02 | 8 | R. with Delay | B | K
BADYA-CON-D6-A1-IR-CIVIL-0188 | 0 | HYPERLINK | L |  | STEEL RFT. FOR GR COLUMNS AT (A1-05-05) | A1-05-05 | 2025-08-25 | 2025-09-02 | 8 | R. with Delay | B | K
BADYA-CON-D6-A1-IR-CIVIL-0189 | 0 | HYPERLINK | L |  | STEEL RFT. FOR GR SLAB AT (A1-06-01) | A1-06-01 | 2025-08-25 | 2025-09-02 | 8 | R. with Delay | B | K
BADYA-CON-D6-A1-IR-CIVIL-0190 | 0 | HYPERLINK | L |  | FORM WORK FOR 1ST COLUMNS OF (A1-06-03) | A1-06-03 | 2025-08-25 | 2025-09-02 | 8 | R. with Delay | B | K
BADYA-CON-D6-A1-IR-CIVIL-0191 | 0 | HYPERLINK | L |  | FORM WORK FOR 1ST COLUMNS OF (A1-06-02) | A1-06-02 | 2025-08-25 | 2025-09-11 | 17 | R. with Delay | B | K
BADYA-CON-D6-A1-IR-CIVIL-0192 | 0 | HYPERLINK | L |  | FORM WORK FOR 1ST COLUMNS OF (A1-06-06) | A1-06-06 | 2025-08-25 | 2025-09-02 | 8 | R. with Delay | B | K
BADYA-CON-D6-A1-IR-CIVIL-0193 | 0 | HYPERLINK | L |  | 2ND COAT OF INSULATION FOR RC FOOTING AT (A1-03-04). | A1-03-04 | 2025-08-25 | 2025-09-11 | 17 | R. with Delay | B | K
BADYA-CON-D6-A1-IR-CIVIL-0194 | 0 | HYPERLINK | L |  | STEEL RFT. FOR THE 1ST COLUMNS OF (A1-05-01) | A1-05-01 | 2025-08-25 | 2025-09-02 | 8 | R. with Delay | B | K
BADYA-CON-D6-A1-IR-CIVIL-0195 | 0 | HYPERLINK | L |  | FORM WORK FOR PC FOOTING AT (A1-04-(04,05)) | A1-04-(04,05) | 2025-08-28 | 2025-09-02 | 5 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0196 | 0 | HYPERLINK | L |  | FORM WORK FOR PC FOOTING AT (A1-04-(06,07,08)) | A1-04-(06,07,08) | 2025-08-28 | 2025-09-02 | 5 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0197 | 0 | HYPERLINK | L |  | FORM WORK FOR PC FOOTING AT (A1-04-(01,02,03)) | A1-04-(01,02,03) | 2025-08-28 | 2025-09-02 | 5 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0198 | 0 | HYPERLINK | L |  | STEEL RFT. FOR THE 1ST COLUMNS OF (A1-06-04) | (A1-06-04 | 2025-08-31 | 2025-09-02 | 2 | Replied | B
BADYA-CON-D6-A1-IR-CIVIL-0199 | 0 | HYPERLINK | L |  | STEEL RFT. FOR GR SLAB AT (A1-06-05) | (A1-06-05 | 2025-08-31 | 2025-09-11 | 11 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0200 | 0 | HYPERLINK | L |  | 1ST COAT OF INSULATION FOR UNDER SOG AT (A1-03-01). | (A1-03-01 | 2025-08-31 | 2025-09-02 | 2 | Replied | B
BADYA-CON-D6-A1-IR-CIVIL-0201 | 0 | HYPERLINK | L |  | 1ST COAT OF INSULATION FOR UNDER SOG AT (A1-03-02). | (A1-03-02 | 2025-08-31 | 2025-09-11 | 11 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0202 | 0 | HYPERLINK | L |  | STEEL RFT. FOR 2ND SLAB AT (A1-05-04) | (A1-03-04 | 2025-09-03 | 2025-09-09 | 6 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0203 | 0 | HYPERLINK | L |  | STEEL RFT. FOR 3RD COLUMNS OF (A1-03-07) | (A1-03-07 | 2025-09-03 | 2025-09-09 | 6 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0204 | 0 | HYPERLINK | L |  | FORM WORK AND STEEL RFT FOR RC FOOTING AT (A1-04-(01,02,03) | (A1-04-(01,02,03) | 2025-09-03 | 2025-09-09 | 6 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0205 | 0 | HYPERLINK | L |  | FORM WORK AND STEEL RFT FOR RC FOOTING AT (A1-04-(04,05) | (A1-04-(04,05) | 2025-09-03 | 2025-09-11 | 8 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0206 | 0 | HYPERLINK | L |  | FORM WORK FOR 1ST SLAB AT (A1-05-06) | (A1-05-06) | 2025-09-03 | 2025-09-09 | 6 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0207 | 0 | HYPERLINK | L |  | FORM WORK FOR 1ST COLUMNS OF (A1-05-01) | (A1-05-01) | 2025-09-03 | 2025-09-09 | 6 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0208 | 0 | HYPERLINK | L |  | STEEL RFT. FOR 1ST COLUMNS AT (A1-05-02) | (A1-05-02) | 2025-09-03 | 2025-09-09 | 6 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0209 | 0 | HYPERLINK | L |  | STEEL RFT. FOR 1ST COLUMNS AT (A1-05-03) | (A1-05-03) | 2025-09-03 | 2025-09-09 | 6 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0210 | 0 | HYPERLINK | L |  | FORM WORK FOR GR COLUMNS OF (A1-05-05) | (A1-05-05) | 2025-09-03 | 2025-09-09 | 6 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0211 | 0 | HYPERLINK | L |  | FORM WORK FOR GR COLUMNS OF (A1-05-04) | (A1-05-04) | 2025-09-03 | 2025-09-11 | 8 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0212 | 0 | HYPERLINK | L |  | Surface Preparation Before Insulation For RC FOOTING AT (A1-05-06). | (A1-05-06) | 2025-09-03 | 2025-09-09 | 6 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0213 | 0 | HYPERLINK | L |  | FORM WORK AND STEEL RFT FOR RC FOOTING AT (A1-04-08) | (A1-04-08) | 2025-09-03 | 2025-09-09 | 6 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0214 | 0 | HYPERLINK | L |  | STEEL RFT. FOR 3RD COLUMNS AT (A1-05-03) | (A1-03-03) | 2025-09-08 | 2025-09-11 | 3 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0215 | 0 | HYPERLINK | L |  | FORM WORK FOR 1ST COLUMNS OF (A1-06-04) | (A1-06-04) | 2025-09-08 | 2025-09-11 | 3 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0216 | 0 | HYPERLINK | L |  | Surface Preparation Before Insulation For RC FOOTING AT (A1-06-06). | (A1-06-06) | 2025-09-08 | 2025-09-11 | 3 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0217 | 0 | HYPERLINK | L |  | STEEL RFT. FOR 2nd slab AT (A1-03-02) | (A1-03-02) | 2025-09-09 | 2025-09-14 | 5 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0218 | 0 | HYPERLINK | L |  | 2ND COAT OF INSULATION FOR MASONARY UDNER SOG AT (A1-03-01). | (A1-03-01) | 2025-09-09 | 2025-09-14 | 5 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0219 | 0 | HYPERLINK | L |  | FORM WORK FOR 1ST SLAB AT (A1-06-03) | (A1-06-03) | 2025-09-09 | 914/2025 | #VALUE! | #VALUE! | B
BADYA-CON-D6-A1-IR-CIVIL-0220 | 0 | HYPERLINK | L |  | FORM WORK FOR 3rd column AT (A1-03-07) | (A1-03-07) | 2025-09-10 | 2025-09-11 | 1 | Replied | B
BADYA-CON-D6-A1-IR-CIVIL-0221 | 0 | HYPERLINK | L |  | FORM WORK FOR 1st column AT (A1-05-03) | (A1-05-03) | 2025-09-10 | 2025-09-11 | 1 | Replied | B
BADYA-CON-D6-A1-IR-CIVIL-0222 | 0 | HYPERLINK | L |  | FORM WORK FOR 1st column AT (A1-05-02) | (A1-05-02) | 2025-09-10 | 2025-09-11 | 1 | Replied | B
BADYA-CON-D6-A1-IR-CIVIL-0223 | 0 | HYPERLINK | L |  | FORM WORK FOR 1st slab AT (A1-05-01) | (A1-05-01) | 2025-09-10 | 2025-09-14 | 4 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0224 | 0 | HYPERLINK | L |  | FORM WORK FOR 1st slab AT (A1-06-06) | (A1-06-06) | 2025-09-10 | 2025-09-14 | 4 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0225 | 0 | HYPERLINK | L |  | STEEL RFT. FOR 3RD COLUMNS AT (A1-03-04) | (A1-03-04) | 2025-09-10 | 2025-09-14 | 4 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0226 | 0 | HYPERLINK | L |  | Surface Preparation Before Insulation For RC FOOTING AT (A1-05-07). | (A1-05-07) | 2025-09-10 | 2025-09-11 | 1 | Replied | B
BADYA-CON-D6-A1-IR-CIVIL-0227 | 0 | HYPERLINK | L |  | STEEL RFT. FOR 1ST slab AT (A1-05-06) | A1-05-06 | 2025-09-11 | 2025-09-14 | 3 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0228 | 0 | HYPERLINK | L |  | 2nd coat of insulation for masonary under SOG AT A1-03-02 | A1-03-02 | 2025-09-13 | 2025-09-18 | 5 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0229 | 0 | HYPERLINK | L |  | 3RD coat of insulation for RC FOOTING SOG AT A1-03-04 | A1-03-04 | 2025-09-13 | 2025-09-18 | 5 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0230 | 0 | HYPERLINK | L |  | FORM WORK FOR 3RD COLUMNS AT (A1-03-03) | A1-03-03 | 2025-09-13 | 2025-09-18 | 5 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0231 | 0 | HYPERLINK | L |  | FORM WORK FOR GR SLAB AT (A1-05-04) | A1-05-04 | 2025-09-13 | 2025-09-18 | 5 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0232 | 0 | HYPERLINK | L |  | STEEL RFT. FOR GR COLUOMN AT (A1-04-03) | A1-04-03 | 2025-09-14 | 2025-09-16 | 2 | Replied | B
BADYA-CON-D6-A1-IR-CIVIL-0233 | 0 | HYPERLINK | L |  | FORM WORK FOR 1ST SLAB AT (A1-05-07) | A1-05-07 | 2025-09-14 | 2025-09-18 | 4 | R. with Delay | B
BADYA-CON-D6-A1-IR-CIVIL-0234 | 0 | HYPERLINK | L |  | Surface Preparation Before Insulation For RC FOOTING AT (A1-06-03). | A1-06-03 | 2025-09-14 | 2025-09-16 | 2 | Replied | B
BADYA-CON-D6-A1-IR-CIVIL-0235 | 0 | HYPERLINK | L |  | STEEL RFT. FOR 1ST COLUOMN AT (A1-06-05) | A1-06-05 | 2025-09-14 | 2025-09-16 | 2 | Replied | B
BADYA-CON-D6-A1-IR-CIVIL-0236 | 0 | HYPERLINK | L |  | 3RD COAT OF INSULATION FOR MASONARY UDNER SOG AT (A1-03-01). | (A1-03-01) | 2025-09-14 | 2025-09-16 | 2 | Replied | B | K
BADYA-CON-D6-A1-IR-CIVIL-0237 | 0 | HYPERLINK | L |  | FORM WORK FOR 3RD COLUMNS AT (A1-03-04) | (A1-03-04) | 2025-09-14 | 2025-09-18 | 4 | R. with Delay | B | K
BADYA-CON-D6-A1-IR-CIVIL-0238 | 0 | HYPERLINK | L |  | STEEL RFT. FOR 1st slab AT (A1-05-01) | (A1-05-01) | 2025-09-14 | 2025-09-16 | 2 | Replied | B | K
BADYA-CON-D6-A1-IR-CIVIL-0239 | 0 | HYPERLINK | L |  | STEEL RFT. FOR 1st slab AT (A1-06-03) | (A1-06-03) | 2025-09-17 | 2025-09-24 |  |  | B
BADYA-CON-D6-A1-IR-CIVIL-0240 | 0 | HYPERLINK | L |  | STEEL RFT. FOR 1st slab AT (A1-06-06) | (A1-06-06) | 2025-09-17 | 2025-09-24 |  |  | B
BADYA-CON-D6-A1-IR-CIVIL-0241 | 0 | HYPERLINK | L |  | FORM WORK AND STEEL RFT FOR RC FOOTING AT (A1-04-06) | (A1-04-06) | 2025-09-17 | 2025-09-24 |  |  | B
BADYA-CON-D6-A1-IR-CIVIL-0242 | 0 | HYPERLINK | L |  | STEEL RFT. FOR GROUND COLUMN AT (A1-04-01) | (A1-04-01) | 2025-09-17 | 2025-09-24 |  |  | B
BADYA-CON-D6-A1-IR-CIVIL-0243 | 0 | HYPERLINK | L |  | STEEL RFT. FOR GROUND COLUMN AT (A1-04-02) | (A1-04-02) | 2025-09-17 | 2025-09-24 |  |  | B
BADYA-CON-D6-A1-IR-CIVIL-0244 | 0 | HYPERLINK | L |  | Surface Preparation Before Insulation For RC FOOTING AT (A1-05-01) | (A1-05-01) | 2025-09-17 | 2025-09-24 |  |  | C
BADYA-CON-D6-A1-IR-CIVIL-0244 | 1 | HYPERLINK | L |  | Surface Preparation Before Insulation For RC FOOTING AT (A1-05-01) | (A1-05-01) | 2025-10-06
BADYA-CON-D6-A1-IR-CIVIL-0245 | 0 | HYPERLINK | L |  | 1ST COAT OF INSULATION FOR RC FOOTING AT (A1-05-06). | (A1-05-06) | 2025-09-17 | 2025-09-24 |  |  | B
BADYA-CON-D6-A1-IR-CIVIL-0246 | 0 | HYPERLINK | L |  | FORM WORK FOR 1ST COLUMNS AT (A1-06-05) | (A1-06-05) | 2025-09-17 | 2025-09-24 |  |  | B
BADYA-CON-D6-A1-IR-CIVIL-0247 | 0 | HYPERLINK | L |  | FORM WORK FOR GROUND COLUMNS AT (A1-04-03) | (A1-04-03) | 2025-09-18 | 2025-09-24 |  |  | B
BADYA-CON-D6-A1-IR-CIVIL-0248 | 0 | HYPERLINK | L |  | 1ST COAT OF INSULATION FOR RC FOOTING AT (A1-06-03). | (A1-06-03) | 2025-09-18 | 2025-09-24 |  |  | B
BADYA-CON-D6-A1-IR-CIVIL-0249 | 0 | HYPERLINK | L |  | STEEL RFT. FOR 2ND COLUMN AT (A1-05-01) | (A1-05-01) | 2025-09-20 | 2025-09-24 |  |  | B
BADYA-CON-D6-A1-IR-CIVIL-0250 | 0 | HYPERLINK | L |  | FORM WORK FOR 1ST SLAB AT (A1-05-02) | (A1-05-02) | 2025-09-20 | 2025-09-29 |  |  | B
BADYA-CON-D6-A1-IR-CIVIL-0251 | 0 | HYPERLINK | L |  | Surface Preparation Before Insulation For RC FOOTING AT (A1-05-02) | (A1-05-02) | 2025-09-21 | 2025-09-24 |  |  | C
BADYA-CON-D6-A1-IR-CIVIL-0251 | 1 | HYPERLINK | L |  | Surface Preparation Before Insulation For RC FOOTING AT (A1-05-02) | (A1-05-02) | 2025-09-25 | 2025-09-29 |  |  | B
BADYA-CON-D6-A1-IR-CIVIL-0252 | 0 | HYPERLINK | L |  | STEEL RFT. FOR 2ND COLUMN AT (A1-05-06) | (A1-05-06) | 2025-09-20
BADYA-CON-D6-A1-IR-CIVIL-0253 | 0 | HYPERLINK | L |  | 1ST COAT OF INSULATION FOR RC FOOTING AT (A1-05-07) | (A1-05-07) | 2025-09-20 | 2025-09-24 |  |  | B
BADYA-CON-D6-A1-IR-CIVIL-0254 | 0 | HYPERLINK | L |  | 3RD COAT OF INSULATION FOR MASONARY UDNER SOG AT (A1-03-02). | (A1-03-02) | 2025-09-20 | 2025-09-24 |  |  | B
BADYA-CON-D6-A1-IR-CIVIL-0255 | 0 | HYPERLINK | L |  | STEEL RFT. FOR GROUND SLAB AT (A1-05-04) | (A1-05-04) | 2025-09-20 | 2025-09-24 |  |  | B
BADYA-CON-D6-A1-IR-CIVIL-0256 | 0 | HYPERLINK | L |  | STEEL RFT. FOR 3RD COLUMNS AT (A1-03-02) | (A1-03-02) | 2025-09-21 | 2025-09-24 |  |  | B
BADYA-CON-D6-A1-IR-CIVIL-0257 | 0 | HYPERLINK | L |  | 2nd COAT OF INSULATION FOR RC FOOTING AT (A1-05-06). | (A1-05-06) | 2025-09-21 | 2025-09-24 |  |  | B
BADYA-CON-D6-A1-IR-CIVIL-0258 | 0 | HYPERLINK | L |  | FORM WORK FOR 3RD SLAB AT (A1-03-07) | (A1-03-07) | 2025-09-22 | 2025-09-25 |  |  | B
BADYA-CON-D6-A1-IR-CIVIL-0259 | 0 | HYPERLINK | L |  | Surface Preparation Before Insulation For RC FOOTING AT (A1-05-03) | (A1-05-03) | 2025-09-22 | 2025-09-25 |  |  | B
BADYA-CON-D6-A1-IR-CIVIL-0260 | 0 | HYPERLINK | L |  | 1ST COAT OF INSULATION FOR RC FOOTING AT (A1-06-06) | (A1-06-06) | 2025-09-22 | 2025-09-25 |  |  | B
BADYA-CON-D6-A1-IR-CIVIL-0261 | 0 | HYPERLINK | L |  | STEEL RFT. FOR 3RD COLUMNS AT (A1-03-01) | (A1-03-01) | 2025-09-23 | 2025-09-29 |  |  | B
BADYA-CON-D6-A1-IR-CIVIL-0262 | 0 | HYPERLINK | L |  | FORM WORK FOR 2nd SLAB AT (A1-03-06) | (A1-03-03) | 2025-09-23 | 2025-09-25 |  |  | B
BADYA-CON-D6-A1-IR-CIVIL-0263 | 0 | HYPERLINK | L |  | FORM WORK FOR GROUND COLUMN AT (A1-04-02) | (A1-04-02) | 2025-09-23 | 2025-09-25 |  |  | B
BADYA-CON-D6-A1-IR-CIVIL-0264 | 0 | HYPERLINK | L |  | STEEL RFT. FOR GROUND COLUMN AT (A1-04-05) | (A1-04-05) | 2025-09-23 | 2025-09-25 |  |  | B
BADYA-CON-D6-A1-IR-CIVIL-0265 | 0 | HYPERLINK | L |  | FORM WORK FOR GROUND SLAB AT (A1-05-05) | (A1-05-05) | 2025-09-23 | 2025-09-29 |  |  | B
BADYA-CON-D6-A1-IR-CIVIL-0266 | 0 | HYPERLINK | L |  | STEEL RFT. FOR 1ST SLAB AT (A1-05-07) | (A1-05-07) | 2025-09-23 | 2025-09-25 |  |  | B
BADYA-CON-D6-A1-IR-CIVIL-0267 | 0 | HYPERLINK | L |  | STEEL RFT. FOR 2ND COLUMN AT (A1-06-03) | (A1-06-03) | 2025-09-23 | 2025-09-27 |  |  | C | H
BADYA-CON-D6-A1-IR-CIVIL-0267 | 1 | HYPERLINK | L |  | STEEL RFT. FOR 2ND COLUMN AT (A1-06-03) | (A1-06-03) | 2025-09-29 |  |  |  |  | H
BADYA-CON-D6-A1-IR-CIVIL-0268 | 0 | HYPERLINK | L |  | STEEL RFT. FOR 2ND COLUMN AT (A1-06-06) | (A1-06-06) | 2025-09-23 | 2025-09-27 |  |  | C | H
BADYA-CON-D6-A1-IR-CIVIL-0268 | 1 | HYPERLINK | L |  | STEEL RFT. FOR 2ND COLUMN AT (A1-06-06) | (A1-06-06) | 2025-09-29 | 2025-10-05 |  |  | B | H
BADYA-CON-D6-A1-IR-CIVIL-0269 | 0 | HYPERLINK | L |  | FORM WORK FOR GROUND COLUMN AT (A1-04-01) | (A1-04-01) | 2025-09-24 | 2025-09-29 |  |  | B
BADYA-CON-D6-A1-IR-CIVIL-0270 | 0 | HYPERLINK | L |  | STEEL RFT. FOR GROUND COLUMN AT (A1-04-04) | (A1-04-04) | 2025-09-24 | 2025-09-29 |  |  | B
BADYA-CON-D6-A1-IR-CIVIL-0271 | 0 | HYPERLINK | L |  | STEEL RFT. FOR 1ST COLUMN AT (A1-06-01) | (A1-06-01) | 2025-09-24 | 2025-09-25 |  |  | B
BADYA-CON-D6-A1-IR-CIVIL-0272 | 0 | HYPERLINK | L |  | FORM WORK FOR 3rd column AT (A1-03-02) | (A1-03-02) | 2025-09-25 | 2025-09-29 |  |  | B
BADYA-CON-D6-A1-IR-CIVIL-0273 | 0 | HYPERLINK | L |  | FORM WORK FOR 2nd column AT (A1-05-01) | (A1-05-01) | 2025-09-25 | 2025-09-29 |  |  | B
BADYA-CON-D6-A1-IR-CIVIL-0274 | 0 | HYPERLINK | L |  | 3rd COAT OF INSULATION FOR RC FOOTING AT (A1-05-06) | (A1-05-06) | 2025-09-25 | 2025-09-29 |  |  | B
BADYA-CON-D6-A1-IR-CIVIL-0275 | 0 | HYPERLINK | L |  | 2nd COAT OF INSULATION FOR RC FOOTING AT (A1-05-07) | (A1-05-07) | 2025-09-25 | 2025-09-29 |  |  | B
BADYA-CON-D6-A1-IR-CIVIL-0276 | 0 | HYPERLINK | L |  | 2nd COAT OF INSULATION FOR RC FOOTING AT (A1-06-03) | (A1-06-03) | 2025-09-25 | 2025-09-29 |  |  | B
BADYA-CON-D6-A1-IR-CIVIL-0277 | 0 | HYPERLINK | L |  | STEEL RFT. FOR 1st COLUMN AT (A1-05-04) | (A1-05-04) | 2025-09-25 | 2025-09-29 |  |  | C | H
BADYA-CON-D6-A1-IR-CIVIL-0277 | 1 |  |  |  | STEEL RFT. FOR 1st COLUMN AT (A1-05-04) | (A1-05-04) | 2025-09-29 | 2025-10-05 |  |  | B | H
BADYA-CON-D6-A1-IR-CIVIL-0278 | 0 | HYPERLINK | L |  | STEEL RFT. FOR 3rd SLAP AT (A1-03-07) | (A1-03-07) | 2025-09-27 | 2025-09-29 |  |  | C | H
BADYA-CON-D6-A1-IR-CIVIL-0278 | 1 |  |  |  | STEEL RFT. FOR 3rd SLAP AT (A1-03-07) | (A1-03-07) | 2025-09-29 | 2025-10-05 |  |  | B | H
BADYA-CON-D6-A1-IR-CIVIL-0279 | 0 | HYPERLINK | L |  | 1ST COAT OF INSULATION FOR RC FOOTING AT (A1-05-03) | (A1-05-03) | 2025-09-27 | 2025-09-29 |  |  | B | H
BADYA-CON-D6-A1-IR-CIVIL-0280 | 0 | HYPERLINK | L |  | 2nd COAT OF INSULATION FOR RC FOOTING AT (A1-06-06) | (A1-06-06) | 2025-09-27 | 2025-09-29 |  |  | B | H
BADYA-CON-D6-A1-IR-CIVIL-0281 | 0 | HYPERLINK | L |  | FORM WORK FOR 3rd slab AT (A1-03-03) | (A1-03-03) | 2025-09-28 | 2025-09-29 |  |  | C | H
BADYA-CON-D6-A1-IR-CIVIL-0281 | 1 | HYPERLINK | L |  | FORM WORK FOR 3rd slab AT (A1-03-03) | (A1-03-03) | 2025-09-29 | 2025-10-05 |  |  | B | H
BADYA-CON-D6-A1-IR-CIVIL-0282 | 0 | HYPERLINK | L |  | FORM WORK FOR GR COLUMN AT (A1-04-05) | (A1-04-05) | 2025-09-28 | 2025-10-05 |  |  | B | H
BADYA-CON-D6-A1-IR-CIVIL-0283 | 0 | HYPERLINK | L |  | FORM WORK FOR 3rd COLUMN AT (A1-03-01) | (A1-03-01) | 2025-09-29 | 2025-10-05 |  |  | B | H
BADYA-CON-D6-A1-IR-CIVIL-0284 | 0 | HYPERLINK | L |  | STEEL RFT. FOR 1st slab AT (A1-05-02) | (A1-05-02) | 2025-09-29 |  |  |  |  | H
BADYA-CON-D6-A1-IR-CIVIL-0285 | 0 | HYPERLINK | L |  | 1ST COAT OF INSULATION FOR RC FOOTING AT (A1-05-02) | (A1-05-02) | 2025-09-29 | 2025-10-05 |  |  | B | H
BADYA-CON-D6-A1-IR-CIVIL-0286 | 0 | HYPERLINK | L |  | 2nd COAT OF INSULATION FOR RC FOOTING AT (A1-05-03) | (A1-05-03) | 2025-09-29 | 2025-10-05 |  |  | B | H
BADYA-CON-D6-A1-IR-CIVIL-0287 | 0 | HYPERLINK | L |  | 3rd COAT OF INSULATION FOR RC FOOTING AT (A1-05-07) | (A1-05-07) | 2025-09-29 | 2025-10-05 |  |  | B | H
BADYA-CON-D6-A1-IR-CIVIL-0288 | 0 | HYPERLINK | L |  | FORM WORK FOR 1st COLUMN AT (A1-06-01) | (A1-06-01) | 2025-09-29 | 2025-10-05 |  |  | B | H
BADYA-CON-D6-A1-IR-CIVIL-0289 | 0 | HYPERLINK | L |  | 3rd COAT OF INSULATION FOR RC FOOTING AT (A1-06-03) | (A1-06-03) | 2025-09-29 | 2025-10-05 |  |  | B | H
BADYA-CON-D6-A1-IR-CIVIL-0290 | 0 | HYPERLINK | L |  | 3rd COAT OF INSULATION FOR RC FOOTING AT (A1-06-06) | (A1-06-06) | 2025-09-29 | 2025-10-05 |  |  | B | H
BADYA-CON-D6-A1-IR-CIVIL-0291 | 0 | HYPERLINK | L |  | FORM WORK FOR GR COLUMN AT (A1-04-04) | (A1-04-04) | 2025-09-30 | 2025-10-05 |  |  | B
BADYA-CON-D6-A1-IR-CIVIL-0292 | 0 | HYPERLINK | L |  | FORM WORK FOR 1st slab AT (A1-06-04) | (A1-06-04) | 2025-09-30 | 2025-10-05 |  |  | B
BADYA-CON-D6-A1-IR-CIVIL-0293 | 0 | HYPERLINK | L |  | Surface Preparation Before Insulation For RC FOOTING AT (A1-06-05) | (A1-06-05) | 2025-09-30 | 2025-10-05 |  |  | C
BADYA-CON-D6-A1-IR-CIVIL-0293 | 1 | HYPERLINK | L |  | Surface Preparation Before Insulation For RC FOOTING AT (A1-06-05) | (A1-06-05) | 2025-10-06 |  |  |  | C
BADYA-CON-D6-A1-IR-CIVIL-0294 | 0 | HYPERLINK | L |  | STEEL RFT. FOR 2nd Slab AT (A1-03-06) | (A1-03-06) | 2025-10-01 | 2025-10-05 |  |  | B | n
BADYA-CON-D6-A1-IR-CIVIL-0295 | 0 | HYPERLINK | L |  | STEEL RFT. FOR Ground Column AT (A1-04-06) | (A1-04-06) | 2025-10-01 | 2025-10-05 |  |  | B | n
BADYA-CON-D6-A1-IR-CIVIL-0296 | 0 | HYPERLINK | L |  | STEEL RFT. FOR 2nd Column AT (A1-05-07) | (A1-05-07) | 2025-10-01 |  |  |  |  | n
BADYA-CON-D6-A1-IR-CIVIL-0297 | 0 | HYPERLINK | L |  | FORM WORK FOR 1st slab AT (A1-06-02) | (A1-06-02) | 2025-10-01 |  |  |  |  | n
BADYA-CON-D6-A1-IR-CIVIL-0298 | 0 | HYPERLINK | L |  | Form Work For 3rd Slab At (A1-03-04) | (A1-03-04) | 2025-10-04 |  |  |  |  | n
BADYA-CON-D6-A1-IR-CIVIL-0299 | 0 | HYPERLINK | L |  | Steel RFT For 2nd Slab At (A-03-05) | (A-03-05) | 2025-10-04 |  |  |  |  | n
BADYA-CON-D6-A1-IR-CIVIL-0300 | 0 | HYPERLINK | L |  | Steel RFT For Ground Slab At (A1-05-05) | (A1-05-05) | 2025-10-04 |  |  |  |  | n
BADYA-CON-D6-A1-IR-CIVIL-0301 | 0 | HYPERLINK | L |  | Form Work 1st Slab At (A1-06-05) | (A1-06-05) | 2025-10-04 |  |  |  |  | n
BADYA-CON-D6-A1-IR-CIVIL-0302 | 0 | HYPERLINK | L |  | Steel RFT For 3rd Slab At (A1-03-03) | (A1-03-03) | 2025-10-06
BADYA-CON-D6-A1-IR-CIVIL-0303 | 0 | HYPERLINK | L |  | STEEL RFT. FOR 4th Column AT (A1-03-07) | (A1-03-07) | 2025-10-06
BADYA-CON-D6-A1-IR-CIVIL-0304 | 0 | HYPERLINK | L |  | Form Work For Ground Column At (A1-04-06) | (A1-04-06) | 2025-10-06
BADYA-CON-D6-A1-IR-CIVIL-0305 | 0 | HYPERLINK | L |  | FORM WORK AND STEEL RFT FOR RC FOOTING AT (A1-04-07) | (A1-04-07) | 2025-10-06
BADYA-CON-D6-A1-IR-CIVIL-0306 | 0 | HYPERLINK | L |  | Steel RFT For Ground Column At (A1-04-08) | (A1-04-08) | 2025-10-06
BADYA-CON-D6-A1-IR-CIVIL-0307 | 0 | HYPERLINK | L |  | FORM WORK FOR Ground slab AT (A1-04-03) | (A1-04-03) | 2025-10-06
BADYA-CON-D6-A1-IR-CIVIL-0308 | 0 | HYPERLINK | L |  | 2nd COAT OF INSULATION FOR RC FOOTING AT (A1-05-02) | (A1-05-02) | 2025-10-06
BADYA-CON-D6-A1-IR-CIVIL-0309 | 0 | HYPERLINK | L |  | 3rd COAT OF INSULATION FOR RC FOOTING AT (A1-05-03) | (A1-05-03) | 2025-10-06
BADYA-CON-D6-A1-IR-CIVIL-0310 | 0 | HYPERLINK | L |  | Form Work For 1st Column At (A1-05-04) | (A1-05-04) | 2025-10-06
BADYA-CON-D6-A1-IR-CIVIL-0311 | 0 | HYPERLINK | L |  | Form Work For 2nd Column At (A1-06-06) | (A1-06-06) | 2025-10-06
BADYA-CON-D6-A1-IR-CIVIL-0312 | 0 | HYPERLINK | L |  | Form Work For 1st slab At (A1-05-03) | (A1-05-03) | 2025-10-08 |  |  |  |  | h
Formulas:
Status = IF([Return Date]="",IF(TODAY()-[Received Date]>(IF([HYPERLINK]=0,S5,S6)),"Overdue","Open"),IF([Return Date]-[Received Date]>(IF([HYPERLINK]=0,P5,P6)),"R. with Delay","Replied"))
Status = IF([Return Date]="",IF(TODAY()-'(IR)-Survey'!H114>(IF([HYPERLINK]=0,S5,S6)),"Overdue","Open"),IF([Return Date]-'(IR)-Survey'!H114>(IF([HYPERLINK]=0,P5,P6)),"R. with Delay","Replied"))

## (IR)-Survey
Open | 0 | #VALUE! | 0% | Inspection Request – (IR) CONTECH Log (Survey) A1 | [6 empty] | Project: |  | Badya
Replied | 86 | #VALUE! | 44.33% | [7 empty] | Contract: |  | 500-004-CC-P8
Overdue | 0 | #VALUE! | 0% | [7 empty] | Contractor: |  | CON.TECH
Reply With Delay | 108 | #VALUE! | 55.67% | [7 empty] | Consultant: |  | Julius Berger International
Total Actions | 194 | #VALUE! | 100% | [7 empty] | Due Date for Submission Rev. = (0) |  |  |  | 2
Within The Allowed Duration (in overdue field) | [10 empty] | Due Date for Submission Rev.>= (1) |  |  |  | 2
Color of the overdue cell will change to yellow when it remains 1 day only for due date | [10 empty] | Dated on |  | 2025-10-09
Inspection Request No | IR Rev. | HYPERLINK | IR Latest Rev. | IR Category | Description | Locion | Received Date | Return Date | DURATION | Status | Multi Action | Ball In Court | Remarks | Soft (PDF) √ - ꓫ | FileNet
BA-CON-D6-A1-IR-SURVY-01 | 0 | HYPERLINK | L | Survy | A1-NGL(LOCATION&LEVEL) | A1 | 2025-02-13 | 2025-02-13 | 0 | Replied | B
BA-CON-D6-A1-IR-SURVY-02 | 0 | HYPERLINK | L | Survy | BOTTOM OF REPLACEMENT AT TRIO-C-M-03 AND COR-C-04 (A1-03) | A1-03-04 | 2025-02-13 | 2025-02-13 | 0 | Replied | A
BA-CON-D6-A1-IR-SURVY-03 | 0 | HYPERLINK | L | Survy | 1ST LAYER OF REPLACEMENT AT TRIO-C-M-03 AND COR-C-04 (A1-03) | A1-03-04 | 2025-02-13 | 2025-02-13 | 0 | Replied | A
BA-CON-D6-A1-IR-SURVY-04 | 0 | HYPERLINK | L | Survy | 2ND LAYER OF REPLACEMENT AT TRIO-C-M-03 AND COR-C-04 (A1-03) | A1-03-04 | 2025-02-13 | 2025-02-13 | 0 | Replied | A
BA-CON-D6-A1-IR-SURVY-05 | 0 | HYPERLINK | L | Survy | 3RD LAYER OF REPLACEMENT AT TRIO-C-M-03 AND COR-C-04 (A1-03) | A1-03-04 | 2025-02-13 | 2025-02-13 | 0 | Replied | A
BA-CON-D6-A1-IR-SURVY-06 | 0 | HYPERLINK | L | Survy | 4TH LAYER OF REPLACEMENT AT TRIO-C-M-03 AND COR-C-04 (A1-03) | A1-03-04 | 2025-02-13 | 2025-02-18 | 5 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-07 | 0 | HYPERLINK | L | Survy | BOTTOM OF REPLACEMENT AT A1-03 (1-2)(5-6-7) | A1-03-01-02-05-06-07 | 2025-02-17 | 2025-02-18 | 1 | Replied | B
BA-CON-D6-A1-IR-SURVY-08 | 0 | HYPERLINK | - | Survy | location and level for excavition border at zone A-1 | A1 | 2025-02-27 | 2025-03-18 | 19 | R. with Delay | C
BA-CON-D6-A1-IR-SURVY-09 | 0 | HYPERLINK | L | Survy | location and level for first layer replacement at A1-03 (1-2) | A1-03-01-02 | 2025-02-27 | 2025-03-03 | 4 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-010 | 0 | HYPERLINK | L | Survy | location and level for Second layer replacement at A1-03 (1-2) | A1-03-01-02 | 2025-02-27 | 2025-03-03 | 4 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-011 | 0 | HYPERLINK | L | Survy | location and level for third layer replacement at A1-03 (1-2) | A1-03-01-02 | 2025-02-27 | 2025-03-03 | 4 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-012 | 0 | HYPERLINK | L | Survy | location and level for first layer replacement at A1-03 (5-6-7) | A1-03-05-06-07 | 2025-02-27 | 2025-03-03 | 4 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-013 | 0 | HYPERLINK | L | Survy | location and level for Second layer replacement at A1-03 (5-6-7) | A1-03-05-06-07 | 2025-02-27 | 2025-03-03 | 4 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-014 | 0 | HYPERLINK | L | Survy | location and level for third layer replacement at A1-03 (5-6-7) | A1-03-05-06-07 | 2025-02-27 | 2025-03-03 | 4 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-015 | 0 | HYPERLINK | L | Survy | location and level for fourth layer replacement at A1-03 (1-2) | A1-03-01-02 | 2025-03-03 | 2025-03-05 | 2 | Replied | B
BA-CON-D6-A1-IR-SURVY-016 | 0 | HYPERLINK | L | Survy | location and level for fifth layer replacement at A1-03 (5-6-7) | A1-03-05-06-07 | 2025-03-03 | 2025-03-05 | 2 | Replied | B
BA-CON-D6-A1-IR-SURVY-017 | 0 | HYPERLINK | L | Survy | location and level for fourth layer replacement at A1-03 (5-6-7) | A1-03-05-06-07 | 2025-03-03 | 2025-03-05 | 2 | Replied | B
BA-CON-D6-A1-IR-SURVY-018 | 0 | HYPERLINK | L | Survy | location and level for bottom level at A1-05 | A1-05 | 2025-03-06 | 2025-03-12 | 6 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-019 | 0 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR FIFTH LAYER AT ZONE A1-03(1-2)BOTTOM PC | A1-03-01-02 | 2025-03-09 | 2025-03-12 | 3 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-020 | 0 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR SIXTH LAYER AT ZONE A1-03(5-6-7) | A1-03-05-06-07 | 2025-03-09 | 2025-03-12 | 3 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-021 | 0 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR FIRST LAYER REPPLACEMENT AT A1-05(4-5) | A1-05-04-05 | 2025-03-13 | 2025-03-16 | 3 | R. with Delay | A
BA-CON-D6-A1-IR-SURVY-022 | 0 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR FIRST LAYER REPPLACEMENT AT A1-05(6-7) | A1-05-06-07 | 2025-03-13 | 2025-03-16 | 3 | R. with Delay | A
BA-CON-D6-A1-IR-SURVY-023 | 0 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR SECOND LAYER REPPLACEMENT AT A1-05(4-5) | A1-05-04-05 | 2025-03-13 | 2025-03-16 | 3 | R. with Delay | A
BA-CON-D6-A1-IR-SURVY-024 | 0 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR SECOND LAYER REPPLACEMENT AT A1-05(6-7) | A1-05-06-07 | 2025-03-13 | 2025-03-16 | 3 | R. with Delay | A
BA-CON-D6-A1-IR-SURVY-025 | 0 | HYPERLINK | L | Survy | location and level for pc at zone A1-03(1-2) | A1-03-01-02 | 2025-03-13 | 2025-03-17 | 4 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-026 | 0 | HYPERLINK | L | Survy | Location and level for pc at zone A1-03(3-4) | A1-03-04 | 2025-03-13 | 2025-03-16 | 3 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-027 | 0 | HYPERLINK | L | Survy | Location and level for rc at zone A1-03(3-4) | A1-03-04 | 2025-03-16 | 2025-03-16 | 0 | Replied | B
BA-CON-D6-A1-IR-SURVY-028 | 0 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR THIRD LAYER REPPLACEMENT AT A1 -05(6-7) | A1-05-06-07 | 2025-03-16 | 2025-03-17 | 1 | Replied | B
BA-CON-D6-A1-IR-SURVY-029 | 0 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR THIRD LAYER REPLACEMENT AT A1-05(1-2) | A1-05-01-02 | 2025-03-16 | 2025-03-17 | 1 | Replied | B
BA-CON-D6-A1-IR-SURVY-030 | 0 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR SECOND LAYER REPLACEMENT AT A1-05(1-2) | A1-05-01-02 | 2025-03-16 | 2025-03-17 | 1 | Replied | B
BA-CON-D6-A1-IR-SURVY-031 | 0 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR FIRST LAYER REPLACEMENT AT A1-05(1-2) | A1-05-01-02 | 2025-03-16 | 2025-03-17 | 1 | Replied | B
BA-CON-D6-A1-IR-SURVY-032 | 0 | HYPERLINK | L | Survy | location point columns A1-03(03-04)offect 30 cm | A1-03-04 | 2025-03-17 | 2025-03-22 | 5 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-033 | 0 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR BOTTOM REPLACEMENT AT A1-06 | A1-06 | 2025-03-17 | 2025-03-22 | 5 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-034 | 0 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR SEVENTH LAYER AT ZONE A1-03(5-6-7)BOTTOM PC LEVEL 235.3 | A1-03(5-6-7) | 2025-03-18 | 2025-03-24 | 6 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-035 | 0 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR FOURTH LAYER REPPLACEMENT AT A1 -05(6-7) | A1 -05(6-7) | 2025-03-19 | 2025-03-24 | 5 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-036 | 0 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR FOURTH LAYER REPLACEMENT AT A1-05(1-2) | A1-05(1-2) | 2025-03-19 | 2025-03-24 | 5 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-037 | 0 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR PC AT ZONE A1-03 BLOCK (5-6-7) | A1-03 BLOCK (5-6-7) | 2025-03-20 | 2025-03-24 | 4 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-038 | 0 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR FIRST LAYER REPLACEMENT AT A1-06 | A1-06 | 2025-03-23 | 2025-03-24 | 4 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-039 | 0 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR FIFTH LAYER REPLACEMENT AT A1-05(1-2).dwg | A1-05(1-2) | 2025-03-25 | 2025-03-25 | 5 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-040 | 0 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR FIFTH LAYER REPPLACEMENT AT A1 -05(6-7) | A1 -05(6-7) | 2025-03-25 | 2025-03-25 | 5 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-041 | 0 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR second LAYER REPLACEMENT AT A1-06 | A1-06 | 2025-03-25 | 2025-03-25 | 5 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-042 | 0 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR THIRD LAYER REPLACEMENT AT A1-06 | A1-06 | 2025-04-08 | 2025-04-10 | 2 | Replied | B
BA-CON-D6-A1-IR-SURVY-043 | 0 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR SIXTH LAYER REPPLACEMENT AT A1 -05(6-7) | A1 -05(6-7) | 2025-04-08 | 2025-04-13 | 5 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-044 | 0 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR SIXTH LAYER REPLACEMENT AT A1-05(1-2). | A1-05(1-2) | 2025-04-08 | 2025-04-10 | 2 | Replied | B
BA-CON-D6-A1-IR-SURVY-045 | 0 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR SEVENTH LAYER REPPLACEMENT AT A1 -05(6-7) | A1 -05(6-7) | 2025-04-13 | 2025-04-13 | 0 | Replied | B
BA-CON-D6-A1-IR-SURVY-046 | 0 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR SEVENTH LAYER REPPLACEMENT AT A1 -05(1-2) | A1-05(1-2) | 2025-04-14 | 2025-04-17 | 3 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-047 | 0 | HYPERLINK | - | Survy | LOCATION AND LEVEL FOR RC AT ZONE A1-03(1-2) | A1-03-01-02 | 2025-04-14 | 2025-04-16 | 2 | Replied | C
BA-CON-D6-A1-IR-SURVY-047 | 1 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR RC AT ZONE A1-03(1-2) | A1-03-01-02 | 2025-04-28 | 2025-04-30 | 2 | Replied | B
BA-CON-D6-A1-IR-SURVY-048 | 0 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR FOURTH LAYER REPLACEMENT AT A1-06 | A1-06 | 2025-04-16 | 2025-04-16 | 0 | Replied | B
BA-CON-D6-A1-IR-SURVY-049 | 0 | HYPERLINK | L | Survy | location and level for pc at zone A1-05(1-2) | A1-05(1-2) | 2025-04-22 | 2025-04-27 | 5 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-050 | 0 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR eighth layer repplacement at A1-05(6-7)LEVEL 237.2 | A1 -05(6-7) | 2025-04-27 | 2025-05-04 | 7 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-051 | 0 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR FIFTH LAYER REPLACEMENT AT A1-06 | A1-06 | 2025-04-27 | 2025-04-27 | 0 | Replied | B
BA-CON-D6-A1-IR-SURVY-052 | 0 | HYPERLINK | L | Survy | location and level for bottom repllacement at A1-04(1-2-3)LEVEL 233.35 | A1-04-1-2-3 | 2025-04-29 | 2025-05-04 | 5 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-053 | 0 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR SIXTH LAYER REPLACEMENT AT A1-06 | A1-06 | 2025-05-01 | 2025-05-04 | 3 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-054 | 0 | HYPERLINK | L | Survy | LOCATION COLLUMS AT A1-03 (1-2) OFFECT .30 | A1-03-01-02 | 2025-05-04 | 2025-05-10 | 6 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-055 | 0 | HYPERLINK | L | Survy | location and level for pc at a1-05(6-7)level 237.5 | A1 -05(6-7) | 2025-05-04 | 2025-05-06 | 2 | Replied | B
BA-CON-D6-A1-IR-SURVY-056 | 0 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR SEVENTH LAYER REPLACEMENT AT A1-06 | A1-06 | 2025-05-06 | 2025-05-06 | 0 | Replied | B
BA-CON-D6-A1-IR-SURVY-057 | 0 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR RC A1-03 ( 5-6-7 ) | A1-03(5-6-7) | 2025-05-08 | 2025-05-11 | 3 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-058 | 0 | HYPERLINK | L | Survy | location columns offect 0.3 at A1-03-(05-06-07) | A1-03(5-6-7) | 2025-05-10 | 2025-05-18 | 8 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-059 | 0 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR FIRST LAYER REPLACEMENT AT ZONE A1-05 (3) LEVEL 235.45 | A1-05 | 2025-05-14 | 2025-05-18 | 4 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-060 | 0 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR SECOND LAYER REPPLACEMENT AT ZONE A1-05 ( 3 ) | A1-05 | 2025-05-14 | 2025-05-18 | 4 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-061 | 0 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR THIRD LAYER REPPLACEMENT AT ZONE A1-05 ( 3 ) | A1-05 | 2025-05-14 | 2025-05-18 | 4 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-062 | 0 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR 8th LAYER REPPLACEMENT AT ZONE A1-06 | A1-06 | 2025-05-20 | 2025-05-21 | 1 | Replied | B | kamal
BA-CON-D6-A1-IR-SURVY-063 | 0 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR PC. AT A1-06 (1-2) | A1-06-01,02 | 2025-05-21 | 2025-05-21 | 0 | Replied | B | kamal
BA-CON-D6-A1-IR-SURVY-064 | 0 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR PC. AT A1-06 (3-4-5-6) | A1-06 (3-4-5-6) | 2025-05-21 | 2025-05-26 | 5 | R. with Delay | B | kamal
BA-CON-D6-A1-IR-SURVY-065 | 0 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR third LAYER REPPACEMENT AT A1-05 (4-5) | A1-05(4-5) | 2025-05-21 | 2025-05-21 | 0 | Replied | B | kamal
BA-CON-D6-A1-IR-SURVY-066 | 0 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR fourth LAYER REPPLACEMENT AT ZONE A1-05 ( 3 ) | A1-05 ( 3 ) | 2025-05-21 | 2025-05-21 | 0 | Replied | B | kamal
BA-CON-D6-A1-IR-SURVY-067 | 0 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR fourth LAYER REPPACEMENT AT A1-05 (4-5) | A1-05(4-5) | 2025-05-21 | 2025-05-21 | 0 | Replied | B | kamal
BA-CON-D6-A1-IR-SURVY-068 | 0 | HYPERLINK | L | Survy | location and level for rc at a1-05 (6-7) | A1-05(6-7) | 2025-05-29 | 2025-06-01 | 3 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-069 | 0 | HYPERLINK | L | Survy | AXIS AND LEVEL for ground slab trio c -m 103.05 at A1-03-07 | A1-03-07 | 2025-06-01 | 2025-06-16 | 15 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-070 | 0 | HYPERLINK | L | Survy | axis and level for ground slab at a1-03-03 | a1-03-03 | 2025-06-01 | 2025-06-16 | 15 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-071 | 0 | HYPERLINK | L | Survy | AXIS AND LEVEL for ground slab trio c -m 103.05 at A1-03-05 | A1-03-05 | 2025-06-15 | 2025-06-16 | 1 | Replied | B
BA-CON-D6-A1-IR-SURVY-072 | 0 | HYPERLINK | L | Survy | EDGE AND LEVEL FOR GROUND SLAB AT TRIO C -M 103.05 AT A1-03-07 | A1-03-07 | 2025-06-15 | 2025-06-16 | 1 | Replied | B
BA-CON-D6-A1-IR-SURVY-073 | 0 | HYPERLINK | L | Survy | LOCATION COLUMNS OFFSET 0.3 AT A1-05-(06-07) | A1-05(6-5) | 2025-06-15 | 2025-06-22 | 7 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-074 | 0 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR fifth LAYER REPPACEMENT AT A1-05 (4-5) | A1-05(4-5) | 2025-06-17 | 2025-06-18 | 1 | Replied | B
BA-CON-D6-A1-IR-SURVY-075 | 0 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR fifth LAYER REPPLACEMENT AT ZONE A1-05 ( 3 ) | A1-05-03 | 2025-06-17 | 2025-06-18 | 1 | Replied | B
BA-CON-D6-A1-IR-SURVY-076 | 0 | HYPERLINK | L | Survy | AXIS AND LEVEL for ground slab trio c 103.05 at A1-03-01 | A1-03-01 | 2025-06-18 | 2025-06-18 | 0 | Replied | B
BA-CON-D6-A1-IR-SURVY-077 | 0 | HYPERLINK | L | Survy | EDGE AND LEVEL FOR GROUND SLAB TRIO C-M 103.05 AT A1-03-03 | A1-03-03 | 2025-06-19 | 2025-06-23 | 4 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-078 | 0 | HYPERLINK | L | Survy | axis and level for ground slab trio C-M 103.05 at A1-03-02 | A1-03-02 | 2025-06-22 | 2025-06-23 | 1 | Replied | B
BA-CON-D6-A1-IR-SURVY-079 | 0 | HYPERLINK | L | Survy | axis columns for ground slab trio c 103.05 at A1-03-07 | A1-03-07 | 2025-06-22 | 2025-06-23 | 1 | Replied | B
BA-CON-D6-A1-IR-SURVY-080 | 0 | HYPERLINK | L | Survy | axis columns for ground slab trio C-M 103.05 at A1-03-03 | A1-03-03 | 2025-06-22 | 2025-06-23 | 1 | Replied | B
BA-CON-D6-A1-IR-SURVY-081 | 0 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR sixth LAYER REPPACEMENT AT A1-05 (4-5) | A1-05 (4-5) | 2025-06-22 | 2025-06-24 | 2 | Replied | B
BA-CON-D6-A1-IR-SURVY-082 | 0 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR sixth LAYER REPPLACEMENT AT ZONE A1-05 ( 3 ) | A1-05-03 | 2025-06-22 | 2025-06-24 | 2 | Replied | B
BA-CON-D6-A1-IR-SURVY-083 | 0 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR RC AT A1-05 ( 1 - 2 ) | A1-05 (1-2) | 2025-06-23 | 2025-06-24 | 1 | Replied | B
BA-CON-D6-A1-IR-SURVY-084 | 0 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR PC AT A1-05 (3) | A1-05 (3) | 2025-06-24 | 2025-06-24 | 0 | Replied | B
BA-CON-D6-A1-IR-SURVY-085 | 0 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR PC AT A1-05 (4-5) | A1-05 (4-5) | 2025-06-24 | 2025-07-01 | 7 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-086 | 0 | HYPERLINK | L | Survy | edge and level for ground slab trio c-m level 103.05 at A1-03-05 | A1-03-05 | 2025-06-24 | 2025-06-24 | 0 | Replied | B
BA-CON-D6-A1-IR-SURVY-087 | 0 | HYPERLINK | L | Survy | location and level for first layer replacement at zone a1-04 | a1-04 | 2025-06-25 | 2025-07-01 | 6 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-088 | 0 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR second layer replacement AT ZONE A1-04 | a1-04 | 2025-06-25 | 2025-07-01 | 6 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-089 | 0 | HYPERLINK | L | Survy | axis columns for ground slab trio C-M 103.05 at A1-03-05 | A1-03-05 | 2025-06-25 | 2025-07-01 | 6 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-090 | 0 | HYPERLINK | L | Survy | EDGE and level for ground slab trio-cm103.05 at a1-03-02 | a1-03-02 | 2025-06-25 | 2025-07-01 | 6 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-091 | 0 | HYPERLINK | L | Survy | location columns offect .30 for rc at a1-05(1-2) | A1-05 (1-2) | 2025-06-25 | 2025-07-01 | 6 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-092 | 0 | HYPERLINK | L | Survy | axis and level for ground slab COR CM 103.05 at a1-03-04 | a1-03-04 | 2025-06-29 | 2025-07-01 | 2 | Replied | B
BA-CON-D6-A1-IR-SURVY-093 | 0 | HYPERLINK | L | Survy | axis and level for ground slab COR CM 103.05 at a1-03-06 | a1-03-06 | 2025-06-29 | 2025-07-01 | 2 | Replied | B
BA-CON-D6-A1-IR-SURVY-094 | 0 | HYPERLINK | L | Survy | edge and level for ground slab at trioc-m 103.05 at a1-03-02 | a1-03-02 | 2025-06-29 | 2025-07-01 | 2 | Replied | B
BA-CON-D6-A1-IR-SURVY-095 | 0 | HYPERLINK | L | Survy | AXIS COLUMNS FOR GROUND SLAB TRIO C-M 103.05 AT A1-03-02 | A1-03-02 | 2025-07-01 | 2025-07-02 | 1 | Replied | B
BA-CON-D6-A1-IR-SURVY-096 | 0 | HYPERLINK | L | Survy | location and level for rc at A1-06 (1-2) | A1-06 (1-2) | 2025-07-01 | 2025-07-02 | 1 | Replied | B
BA-CON-D6-A1-IR-SURVY-097 | 0 | HYPERLINK | L | Survy | location and level for rc at A1-06(3-4-5-6) | A1-06(3-4-5-6) | 2025-07-01 | 2025-07-08 | 7 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-098 | 0 | HYPERLINK | L | Survy | edge and level for ground slab COR CM 103.05 at a1-03-06 | a1-03-06 | 2025-07-01 | 2025-07-02 | 1 | Replied | B
BA-CON-D6-A1-IR-SURVY-099 | 0 | HYPERLINK | L | Survy | edge and level for ground slab COR CM 103.05 at a1-03-04 | a1-03-04 | 2025-07-02 | 2025-07-03 | 1 | Replied | B
BA-CON-D6-A1-IR-SURVY-010 | 0 | HYPERLINK | L | Survy | axis columns for ground slab COR CM 103.05 at a1-03-06 | a1-03-06 | 2025-07-05 | 2025-07-08 | 3 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-0101 | 0 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR fourth layer replacement AT ZONE A1-04 | A1-04 | 2025-07-05 | 2025-07-08 | 3 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-0102 | 0 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR third layer replacement AT ZONE A1-04 | A1-04 | 2025-07-05 | 2025-07-08 | 3 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-0103 | 0 | HYPERLINK | L | Survy | axis columns for ground slab COR CM 103.05 at a1-03-04 | a1-03-04 | 2025-07-05 | 2025-07-08 | 3 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-0104 | 0 | HYPERLINK | L | Survy | location columns offset .30 for RC at A1-06(1-2) | A1-06-01,02 | 2025-07-07 | 2025-07-13 | 6 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-0105 | 0 | HYPERLINK | L | Survy | location columns offset .30 for RC at a1-06(3-4-5-6) | A1-06-3,4,5,6 | 2025-07-07 | 2025-07-13 | 6 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-0106 | 0 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR fifth layer replacement AT ZONE A1-04(1-2-3) level 234.6 | A1-04(1-2-3) level 234.6 | 2025-07-09 | 2025-07-13 | 4 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-0107 | 0 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR FIFTH layer replacement AT ZONE A1-04 (4-5-6-7-8 ) LEVEL 235.35 | A1-04 (4-5-6-7-8 ) LEVEL 235.35 | 2025-07-09 | 2025-07-13 | 4 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-0108 | 0 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR SIXTH layer replacement AT ZONE A1-04 (4-5-6-7-8 ) LEVEL 235.60 | A1-04 (4-5-6-7-8 ) LEVEL 235.60 | 2025-07-09 | 2025-07-21 | 12 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-0109 | 0 | HYPERLINK | L | Survy | axis and level for ground slab 106.05 TRIO C at A1-03 (7) | A1-03 (7) | 2025-07-09 | 2025-07-13 | 4 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-0110 | 0 | HYPERLINK | L | Survy | axis and level for ground slab 106.05 TRIO C-M at A1-03 (3) | A1-03 (3) | 2025-07-09 | 2025-07-13 | 4 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-0111 | 0 | HYPERLINK | L | Survy | axis and level for ground slab 106.05 TRIO C-M at A1-03 (5) | A1-03 (5) | 2025-07-09 | 2025-07-13 | 4 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-0112 | 0 | HYPERLINK | L | Survy | axis and level for ground slab 103.05 TRIO D at A1-05(6-7) | A1-05(6-7) | 2025-07-09 | 2025-07-13 | 4 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-0113 | 0 | HYPERLINK | L | Survy | EDGE and level for FIRST slab 106.05 TRIO C at A1-03 (7) | A1-03 (7) | 2025-07-10 | 2025-07-13 | 3 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-0114 | 0 | HYPERLINK | L | Survy | location and level for RC at a1-05 (3) | a1-05 (3) | 2025-07-14 | 2025-07-16 | 2 | Replied | B
BA-CON-D6-A1-IR-SURVY-0115 | 0 | HYPERLINK | L | Survy | axis and level for 1st slab 106.05 cor c-m at A1-03-06 | A1-03-06 | 2025-07-15 | 2025-07-16 | 1 | Replied | B
BA-CON-D6-A1-IR-SURVY-0116 | 0 | HYPERLINK | L | Survy | axis and level for 1st slab 106.05 TRIO C at A1-03-01 | A1-03-01 | 2025-07-15 | 2025-07-16 | 1 | Replied | B
BA-CON-D6-A1-IR-SURVY-0117 | 0 | HYPERLINK | L | Survy | axis COLUMNS for 1st slab 106.05 TRIO C at A1-03-07 | A1-03-07 | 2025-07-15 | 2025-07-20 | 5 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-0118 | 0 | HYPERLINK | L | Survy | location columns offset .30 for RC at a1-05 (3) | A1-05 (3) | 2025-07-16 | 2025-07-20 | 4 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-0119 | 0 | HYPERLINK | L | Survy | eadge and level for 1st slab 106.05 TRIO C-M at A1-03 (3) | A1-03 (3) | 2025-07-20 | 2025-07-21 | 1 | Replied | B
BA-CON-D6-A1-IR-SURVY-0120 | 0 | HYPERLINK | L | Survy | eadge and level for 1st slab 106.05 TRIO C-M at A1-03 (5) | A1-03 (5) | 2025-07-20 | 2025-07-21 | 1 | Replied | B
BA-CON-D6-A1-IR-SURVY-0121 | 0 | HYPERLINK | L | Survy | axis and level for 1st slab 106.05 TRIO Cm at A1-03-02 | A1-03-02 | 2025-07-20 | 2025-07-21 | 1 | Replied | B
BA-CON-D6-A1-IR-SURVY-0122 | 0 | HYPERLINK | L | Survy | axis columns for 1st slab 106.05 TRIO C-M at A1-03 (3) | A1-03-03 | 2025-07-21 | 2025-07-24 | 3 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-0123 | 0 | HYPERLINK | L | Survy | LOCATION AND LEVEL FOR PC AT A1-04 | A1-04 | 2025-07-21 | 2025-07-30 | 9 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-0124 | 0 | HYPERLINK | L | Survy | axis and level for 1st slab 106.05 cor c at A1-03-04 | A1-03-04 | 2025-07-22 | 2025-07-28 | 6 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-0125 | 0 | HYPERLINK | L | Survy | axis and level for ground slab 103.05 TRIO D-m at A1-05-1 | A1-05-1 | 2025-07-22 | 2025-07-28 | 6 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-0126 | 0 | HYPERLINK | L |  | axis and level for ground slab CORC 103.05 at a1-05-02 | A1-05-2 | 2025-07-26 | 2025-07-28 | 2 | Replied | B | K
BA-CON-D6-A1-IR-SURVY-0127 | 0 | HYPERLINK | L |  | edge and level for ground slab 103.05 TRIO D at A1-05-6 | A1-05-06 | 2025-07-26 | 2025-07-30 | 4 | R. with Delay | B | K
BA-CON-D6-A1-IR-SURVY-0128 | 0 | HYPERLINK | L |  | edge and level for 1st slab 106.05 TRIO C at A1-03-1 | A1-03-01 | 2025-07-26 | 2025-07-28 | 2 | Replied | B | K
BA-CON-D6-A1-IR-SURVY-0129 | 0 | HYPERLINK | L |  | axis columns for 1st slab 106.05 TRIO C-M at A1-03 -5 | A1-03-05 | 2025-07-26 | 2025-07-28 | 2 | Replied | B | K
BA-CON-D6-A1-IR-SURVY-0130 | 0 | HYPERLINK | L |  | axis columns for 1st slab 106.05 TRIO C at A1-03-01 | A1-03-01 | 2025-07-26 | 2025-07-30 | 4 | R. with Delay | B | K
BA-CON-D6-A1-IR-SURVY-0131 | 0 | HYPERLINK | L |  | axis and level for ground slab cor c-m 103.05 at A1-06-06 | A1-06-06 | 2025-07-28 | 2025-07-30 | 2 | Replied | B
BA-CON-D6-A1-IR-SURVY-0132 | 0 | HYPERLINK | L |  | axis and level for ground slab DUO-C 103.05 AT A1-06-02 | A1-06-02 | 2025-07-28 | 2025-07-30 | 2 | Replied | B
BA-CON-D6-A1-IR-SURVY-0133 | 0 | HYPERLINK | L |  | axis and level for ground slab 103.05 TRIO D at A1-06-03 | A1-06-03 | 2025-07-29 | 2025-07-30 | 1 | Replied | B
BA-CON-D6-A1-IR-SURVY-0134 | 0 | HYPERLINK | L |  | EDGE and level for 1st slab 106.05 cor c-m at A1-03-06 | A1-03-06 | 2025-07-30 | 2025-08-06 | 7 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-0135 | 0 | HYPERLINK | L |  | Edge and level for ground slab TRIO-D 103.05 at A1-05-07 | A1-05-07 | 2025-07-30 | 2025-08-06 | 7 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-0136 | 0 | HYPERLINK | L |  | Edge and level for first slab trio c-m 106.05 at A1-03-02 | A1-03-02 | 2025-07-30 | 2025-08-06 | 7 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-0137 | 0 | HYPERLINK | L |  | AXIS COLUMNS for ground slab TRIOD at A1-05-06 | A1-05-06 | 2025-07-30 | 2025-08-10 | 11 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-0138 | 0 | HYPERLINK | L |  | Axis columns for 1ST slab cor c-m 106.05 at A1-03-06 | A1-03-06 | 2025-08-02 | 2025-08-05 | 3 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-0139 | 0 | HYPERLINK | L |  | Axis columns for first slab trio c-m 106.05 at A1-03-02 | A1-03-02 | 2025-08-02 | 2025-08-05 | 3 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-0140 | 0 | HYPERLINK | L |  | Axis columns for GROUND slab trio D 103.05 at A1-05-07 | A1-05-07 | 2025-08-02 | 2025-08-05 | 3 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-0141 | 0 | HYPERLINK | L |  | axis and level for ground slab corc 103.05 at a1-06-04 | A1-06-04 | 2025-08-04 | 2025-08-06 | 2 | Replied | B
BA-CON-D6-A1-IR-SURVY-0142 | 0 | HYPERLINK | L |  | axis and level for second slab trio-c 109.05 at a1-03-07 | A1-03-07 | 2025-08-04 | 2025-08-10 | 6 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-0143 | 0 | HYPERLINK | L |  | edge and level for 1st slab cor-c at a1-03-04 | A1-03-04 | 2025-08-04 | 2025-08-10 | 6 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-0144 | 0 | HYPERLINK | L |  | axis columns for 1st cor-c 106.05 at A1-03-04 | A1-03-04 | 2025-08-06 | 2025-08-13 | 7 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-0145 | 0 | HYPERLINK | L |  | axis and level for ground slab 103.05 trioD at A1-05-03 | A1-05-03 | 2025-08-06 | 2025-08-10 | 4 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-0146 | 0 | HYPERLINK | L |  | axis and level for ground slab 103.05 trioDM at A1-06-05 | A1-06-05 | 2025-08-06 | 2025-08-10 | 4 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-0147 | 0 | HYPERLINK | L |  | axis and level for ground slab CORCm 103.05 at a1-06-06 | A1-06-06 | 2025-08-07 | 2025-08-10 | 3 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-0148 | 0 | HYPERLINK | L |  | edge and level for ground slab 103.05 TRIO D at A1-06-03 | A1-06-03 | 2025-08-09 | 2025-08-13 | 4 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-0149 | 0 | HYPERLINK | L |  | edge and level for ground slab corc-m 103.05 at a1-06-06 | A1-06-06 | 2025-08-09 | 2025-08-13 | 4 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-0150 | 0 | HYPERLINK | L |  | axis and level for 2ND SLAB 109.05 TRIO C-m at A1-03-03 | A1-03-03 | 2025-08-09 | 2025-08-13 | 4 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-0151 | 0 | HYPERLINK | L |  | axis and level for ground slab 103.05 DUCM at a1-06-01 | A1-06-01 | 2025-08-11 | 2025-08-20 | 9 | R. with Delay | B | K
BA-CON-D6-A1-IR-SURVY-0152 | 0 | HYPERLINK | L |  | axis columns for ground slab 103.05 TRIO D at A1-06-03 | A1-06-03 | 2025-08-11 | 2025-08-17 | 6 | R. with Delay | B | K
BA-CON-D6-A1-IR-SURVY-0153 | 0 | HYPERLINK | L |  | axis columns for ground slab corc-m 103.05 at a1-06-06 | A1-06-06 | 2025-08-11 | 2025-08-17 | 6 | R. with Delay | B | K
BA-CON-D6-A1-IR-SURVY-0154 | 0 | HYPERLINK | L |  | edge and level for ground slab 103.05 DUC at a1-06-02 | A1-06-02 | 2025-08-11 | 2025-08-13 | 2 | Replied | B
BA-CON-D6-A1-IR-SURVY-0155 | 0 | HYPERLINK | L |  | ASBUILT LEVEL FOR BOTTOM FIRST SLAB AT A1-03-03 | A1-03-03 | 2025-08-12 | 2025-08-13 | 1 | Replied | B
BA-CON-D6-A1-IR-SURVY-0156 | 0 | HYPERLINK | L |  | AXIS AND LEVEL FOR SECOND SLAB TRIO C 109.05 AT A1-03-01 | A1-03-01 | 2025-08-13 | 2025-08-17 | 4 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-0157 | 0 | HYPERLINK | L |  | AXIS AND LEVEL FOR SECOND SLAB TRIO CM 109.05 AT A1-03-05 | A1-03-05 | 2025-08-13 | 2025-08-20 | 7 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-0158 | 0 | HYPERLINK | L |  | axis columns for ground slab 103.05 corc at A1-06-04 | A1-06-04 | 2025-08-13 | 2025-08-25 | 12 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-0159 | 0 | HYPERLINK | L |  | edge and level for ground slab cor c 103.05 at A1-05-02 | A1-05-02 | 2025-08-13 | 2025-08-25 | 12 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-0160 | 0 | HYPERLINK | L |  | edge and level for ground slab trio Dm 103.05 at a1-05-01 | A1-05-01-02 | 2025-08-17 | 2025-08-20 | 3 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-0161 | 0 | HYPERLINK | L |  | location and level for rc at a1-05 (4-5 ) | A1-05-04-05 | 2025-08-17 | 2025-08-17 | 0 | Replied | B
BA-CON-D6-A1-IR-SURVY-0162 | 0 | HYPERLINK | L |  | axis columns for ground slab trioDM 103.05 AT A1-05-01 | A1-05-01 | 2025-08-18 | 2025-08-20 | 2 | Replied | B
BA-CON-D6-A1-IR-SURVY-0163 | 0 | HYPERLINK | L |  | EDGE and level for ground slab 103.05 COR C AT A1-06-04 | A1-06-04 | 2025-08-18 | 2025-08-20 | 2 | Replied | B
BA-CON-D6-A1-IR-SURVY-0164 | 0 | HYPERLINK | L |  | EDGE and level for ground slab 103.05 trio d at A1-05-03 | A1-05-03 | 2025-08-20 | 2025-08-20 | 0 | Replied | B
BA-CON-D6-A1-IR-SURVY-0165 | 0 | HYPERLINK | L |  | axis and level for second slab 109.05 trio-cm at A1-03-02 | A1-03-02 | 2025-08-20 | 2025-08-25 | 5 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-0166 | 0 | HYPERLINK | L |  | axis and level for first slab 106.05 trio-d at A1-05-06 | A1-05-06 | 2025-08-21 | 2025-08-26 | 5 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-0167 | 0 | HYPERLINK | L |  | EDGE and level for second slab 109.05 trio-c at A1-03-07 | A1-03-07 | 2025-08-21 | 2025-08-25 | 4 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-0168 | 0 | HYPERLINK | L |  | 1ST SLAB LEVEL AT A1-05-06(106.05) | A1-05-06 | 2025-08-25 | 2025-08-28 | 3 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-0169 | 0 | HYPERLINK | L |  | 2ND SLAB LEVEL AT A1-03-04(109.05) | A1-03-04 | 2025-08-25 | 2025-08-28 | 3 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-0170 | 0 | HYPERLINK | L |  | 2ND SLAB LEVEL AT A1-03-06(109.05) | A1-03-06 | 2025-08-25 | 2025-08-28 | 3 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-0171 | 0 | HYPERLINK | L |  | SLAB EDGE LOCATION & LEVEL AT A1-06-01(103.05) | A1-06-01 | 2025-08-25 | 2025-08-28 | 3 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-0172 | 0 | HYPERLINK | L |  | 2ND SLAB EDGE LOCATION AT A1-03-03(109.05) | A1-03-03 | 2025-08-25 | 2025-08-28 | 3 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-0173 | 0 | HYPERLINK | L |  | RC LOCATION & LEVEL AT A1-04(01,02,03) | A1-04(01,02,03) | 2025-08-26 | 2025-08-28 | 2 | Replied | B
BA-CON-D6-A1-IR-SURVY-0174 | 0 | HYPERLINK | L |  | 1ST SLAB LEVEL & LOCATION AT A1-05-07(106.05) | A1-05-07 | 2025-08-27 | 2025-09-02 | 6 | R. with Delay | C
BA-CON-D6-A1-IR-SURVY-0174 | 1 | HYPERLINK | L |  | 1ST SLAB LEVEL & LOCATION AT A1-05-07(106.05) | A1-05-07 | 2025-09-03 | 2025-09-03 | 0 | Replied | B
BA-CON-D6-A1-IR-SURVY-0175 | 0 | HYPERLINK | L |  | axis and level for ground slab 103.05 trio D-M at a1-05-04 | a1-05-04 | 2025-08-31 | 2025-09-02 | 2 | Replied | B
BA-CON-D6-A1-IR-SURVY-0176 | 0 | HYPERLINK | L |  | axis and level for second slab 109.05 cor-cm at A1-03-06 | A1-03-06 | 2025-08-31 | 2025-09-02 | 2 | Replied | B
BA-CON-D6-A1-IR-SURVY-0177 | 0 | HYPERLINK | L |  | AXIS COLUMNS for ground slab 103.05 trio d at A1-05-03 | A1-05-03 | 2025-08-31 | 2025-09-01 | 1 | Replied | B
BA-CON-D6-A1-IR-SURVY-0178 | 0 | HYPERLINK | L |  | AXIS COLUMNS for 2nd slab 109.05 trio -cm at A1-03-03 | A1-03-03 | 2025-08-31 | 2025-09-01 | 1 | Replied | B
BA-CON-D6-A1-IR-SURVY-0179 | 0 | HYPERLINK | L |  | AXIS COLUMNS for ground slab 103.05 COR C AT A1-06-04 | A1-06-04 | 2025-08-31 | 2025-09-01 | 1 | Replied | B
BA-CON-D6-A1-IR-SURVY-0180 | 0 | HYPERLINK | L |  | AXIS COLUMNS for ground slab 103.05 DUO-CM AT A1-06-01 | A1-06-01 | 2025-08-31 | 2025-09-01 | 1 | Replied | B
BA-CON-D6-A1-IR-SURVY-0181 | 0 | HYPERLINK | L |  | AXIS COLUMNS for ground slab cor c 103.05 at A1-05-02 | A1-05-02 | 2025-08-31 | 2025-09-01 | 1 | Replied | B
BA-CON-D6-A1-IR-SURVY-0182 | 0 | HYPERLINK | L |  | AXIS COLUMNS for second slab 109.05 trio-c at A1-03-07 | A1-03-07 | 2025-08-31 | 2025-09-01 | 1 | Replied | B
BA-CON-D6-A1-IR-SURVY-0183 | 0 | HYPERLINK | L |  | location ofest .30 for rc at a1-05 (4-5 ) | a1-05 | 2025-08-31 | 2025-09-01 | 1 | Replied | B
BA-CON-D6-A1-IR-SURVY-0184 | 0 | HYPERLINK | L |  | location and level for rc at a1-04 (8) | a1-04 | 2025-09-01 | 2025-09-02 | 1 | Replied | B
BA-CON-D6-A1-IR-SURVY-0185 | 0 | HYPERLINK | L |  | AXIS AND LEVEL FOR FIRST SLAB TRIO-DM 106.05AT A1-06-03 | A1-06-03 | 2025-09-01 | 2025-09-02 | 1 | Replied | B
BA-CON-D6-A1-IR-SURVY-0186 | 0 | HYPERLINK | L |  | edge and level for second slab cor-c 109.05 at A1-06-03 | A1-06-03 | 2025-09-01 | 2025-09-02 | 1 | Replied | B
BA-CON-D6-A1-IR-SURVY-0187 | 0 | HYPERLINK | L |  | LOCATION OFSET .30 FOR COLUMNS RC AT A1-04(1-2-3) | A1-04(1-2-3) | 2025-09-01 | 2025-09-09 | 8 | R. with Delay | B
BA-CON-D6-A1-IR-SURVY-0188 | 0 | HYPERLINK | L |  | location and level for rc at a1-04 (4-5) | a1-04 (4-5) | 2025-09-02 | 2025-09-03 | 1 | Replied | B
BA-CON-D6-A1-IR-SURVY-0189 | 0 | HYPERLINK | L |  | axis columns for ground slab 103.05 duo-c at A1-06-02 | A1-06-02 | 2025-09-03 | 2025-09-03 | 0 | Replied | B
BA-CON-D6-A1-IR-SURVY-0190 | 0 | HYPERLINK | L |  | axis and level for first slab cor -cm 106.05 at A1-06-06 | A1-06-06 | 2025-09-03 | 2025-09-03 | 0 | Replied | B
BA-CON-D6-A1-IR-SURVY-0191 | 0 | HYPERLINK | L |  | axis and level for first slab trio-DM 106.05 at A1-05-01 | A1-05-01 | 2025-09-03 | 2025-09-03 | 0 | Replied | B
BA-CON-D6-A1-IR-SURVY-0192 | 0 | HYPERLINK | L |  | AXIS columns second slab 109.05 corc at A1-03-04 | A1-03-04 | 2025-09-06 | 2025-09-07 | 1 | Replied | B | k
BA-CON-D6-A1-IR-SURVY-0193 | 0 | HYPERLINK | L |  | LOCATION ofset .30 for columns rc at a1-04 (4-5-8-6) | A1-04 | 2025-09-09 | 2025-09-15 |  |  | B
BA-CON-D6-A1-IR-SURVY-0194 | 0 | HYPERLINK | L |  | edge and level for 2nd slab trio-cm 109.05 at A1-03-02 | A1-03-02 | 2025-09-09 | 2025-09-11 |  |  | B
BA-CON-D6-A1-IR-SURVY-0195 | 0 | HYPERLINK | L |  | axis and level for ground slab cor-cm 103.05 at A1-05-05 | A1-05-05 | 2025-09-10 | 2025-09-11 |  |  | B
BA-CON-D6-A1-IR-SURVY-0196 | 0 | HYPERLINK | L |  | axis and level for first slab cor-c 106.05 at A1-05-02 | A1-05-02 | 2025-09-14 | 2025-09-15 |  |  | B | K
BA-CON-D6-A1-IR-SURVY-0197 | 0 | HYPERLINK | L |  | LOCATION AND LEVEL FOR RC AT A1-04 PART 06 | PART 06 | 2025-09-14 | 2025-09-15 |  |  | B | K
BA-CON-D6-A1-IR-SURVY-0198 | 0 | HYPERLINK | L |  | edge and level for first slab trio-d 106.05 at A1-05-06 | A1-05-06 | 2025-09-14 | 2025-09-15 |  |  | B | K
BA-CON-D6-A1-IR-SURVY-0199 | 0 | HYPERLINK | L |  | edge and level for first slab trio-DM 106.05 at A1-05-01 | A1-05-01 | 2025-09-14 | 2025-09-15 |  |  | B | K
BA-CON-D6-A1-IR-SURVY-0200 | 0 | HYPERLINK | L |  | axis and level for 4th slab trioc 112.05 at A1-03-07 | A1-03-07 | 2025-09-15 | 2025-09-15 |  |  | B | h
BA-CON-D6-A1-IR-SURVY-0201 | 0 | HYPERLINK | L |  | axis and level for first slab DUOC 106.05 at A1-06-02 | A1-06-02 | 2025-09-15 | 2025-09-21 |  |  | B | h
BA-CON-D6-A1-IR-SURVY-0202 | 0 | HYPERLINK | L |  | AXIS COLUMNS FOR FIRST SLAB TRIOD 106.05 AT A1-05-06 | A1-05-06 | 2025-09-15 | 2025-09-15 |  |  | B | h
BA-CON-D6-A1-IR-SURVY-0203 | 0 | HYPERLINK | L |  | edge and level for first slab cor-cm at A1-06-06 | A1-06-06 | 2025-09-15 | 2025-09-17 |  |  | B | h
BA-CON-D6-A1-IR-SURVY-0204 | 0 | HYPERLINK | L |  | edge and level for first slab trio-DM 106.05 at A1-06-03 | A1-06-03 | 2025-09-15 | 2025-09-15 |  |  | B | h
BA-CON-D6-A1-IR-SURVY-0205 | 0 | HYPERLINK | L |  | edge and level for ground slab trio-DM 103.05 at A1-05-04 | A1-05-04 | 2025-09-15 | 2025-09-15 |  |  | B | h
BA-CON-D6-A1-IR-SURVY-0206 | 0 | HYPERLINK | L |  | edge and level for second slab trio-c 109.05 at A1-03-01 | A1-03-01 | 2025-09-15 | 2025-09-15 |  |  | B | h
BA-CON-D6-A1-IR-SURVY-0207 | 0 | HYPERLINK | L |  | F.F.L +1M FOR GROUND FLOOR BLOCK A1-03-(05-06-07) | A1-03-(05-06-07) | 2025-09-16 | 2025-09-17 |  |  | A
BA-CON-D6-A1-IR-SURVY-0208 | 0 | HYPERLINK | L |  | F.F.L +1M FOR GROUND FLOOR BLOCK A1-03-(01-02) | A1-03-(01-02) | 2025-09-16 | 2025-09-17 |  |  | A
BA-CON-D6-A1-IR-SURVY-0209 | 0 | HYPERLINK | L |  | F.F.L +1M FOR GROUND FLOOR BLOCK A1-03-(03-04) | A1-03-(03-04) | 2025-09-16 | 2025-09-20 |  |  | A
BA-CON-D6-A1-IR-SURVY-0210 | 0 | HYPERLINK | L |  | edge and level for ground slab 103.05 TRIO-DM AT A1-06-05 | A1-06-05 | 2025-09-17 | 2025-09-17 |  |  | B
BA-CON-D6-A1-IR-SURVY-0211 | 0 | HYPERLINK | L |  | AXIS COLUMNS ground slab 103.05 TRIO-DM AT A1-06-05 | A1-06-05 | 2025-09-17 | 2025-09-20 |  |  | B
BA-CON-D6-A1-IR-SURVY-0212 | 0 | HYPERLINK | L |  | AXIS COLUMNS for first slab trio-dm 106.05 at A1-05-01 | A1-05-01 | 2025-09-17 | 2025-09-18 |  |  | B
BA-CON-D6-A1-IR-SURVY-0213 | 0 | HYPERLINK | L |  | AXIS COLUMNS for first slab trio-dm 106.05 at A1-06-03 | A1-06-03 | 2025-09-17 | 2025-09-18 |  |  | B
BA-CON-D6-A1-IR-SURVY-0214 | 0 | HYPERLINK | L |  | axis and level for 3rd slab Trio-cm 112.05 at A1-03-03 | A1-03-03 | 2025-09-23 | 2025-09-24 |  |  | B
BA-CON-D6-A1-IR-SURVY-0215 | 0 | HYPERLINK | L |  | AXIS COLUMNS FOR SECOND SLAB TRIO-C 109.05 AT A1-03-01 | A1-03-01 | 2025-09-18 | 2025-09-18 |  |  | B
BA-CON-D6-A1-IR-SURVY-0216 | 0 | HYPERLINK | L |  | axis columns for first slab 106.05 cor -cm at A1-06-06 | A1-06-06 | 2025-09-20 | 2025-09-21 |  |  | B
BA-CON-D6-A1-IR-SURVY-0217 | 0 | HYPERLINK | L |  | axis columns for ground slab 103.05 trio-dm at A1-05-04 | A1-05-06 | 2025-09-20 | 2025-09-21 |  |  | B
BA-CON-D6-A1-IR-SURVY-0218 | 0 | HYPERLINK | L |  | axis columns for first slab 106.05 cor -c at A1-06-04 | A1-06-04 | 2025-09-20 | 2025-09-21 |  |  | B
BA-CON-D6-A1-IR-SURVY-0219 | 0 | HYPERLINK | L |  | axis columns for first slab 106.05 trio-d at A1-05-07 | A1-05-07 | 2025-09-24 | 2025-09-29 |  |  | B
BA-CON-D6-A1-IR-SURVY-0220 | 0 | HYPERLINK | L |  | axis and level for 3rd slab COR-C 112.05 at A1-03-04 | A1-03-04 | 2025-09-25 | 2025-09-28 |  |  | B
BA-CON-D6-A1-IR-SURVY-0221 | 0 | HYPERLINK | L |  | axis and level for first slab 106.05 trio-d at A1-05-03 | A1-05-03 | 2025-09-25 | 2025-09-28 |  |  | B
BA-CON-D6-A1-IR-SURVY-0222 | 0 | HYPERLINK | L |  | axis and level for first slab 106.05 trio-dm at A1-06-05 | A1-06-05 | 2025-09-25 | 2025-09-28 |  |  | B
BA-CON-D6-A1-IR-SURVY-0223 | 0 | HYPERLINK | L |  | edge and level for 3rd slab 112.05 trio-c at A1-03-07 | A1-03-07 | 9/27/20253 | 2025-09-28 |  |  | B
BA-CON-D6-A1-IR-SURVY-0224 | 0 | HYPERLINK | L |  | EDGE and level for first slab 106.05 cor-c at A1-05-02 | A1-05-02 | 2025-09-28 | 2025-09-28 |  |  | B
BA-CON-D6-A1-IR-SURVY-0225 | 0 | HYPERLINK | L |  | axis and level for ground slab 103.05 cor -cm at A1-04-03 | A1-04-03 | 2025-09-28 | 2025-09-30 |  |  | B | H
BA-CON-D6-A1-IR-SURVY-0226 | 0 | HYPERLINK | L |  | axis columns for first slab 106.05 cor-c at A1-05-02 | at A1-05-02 | 2025-09-29 | 2025-09-30 |  |  | B | H
BA-CON-D6-A1-IR-SURVY-0227 | 0 | HYPERLINK | L |  | axis columns for 3rd slab 112.05 trio-c at A1-03-07 | A1-03-07 | 2025-10-01 | 2025-10-02 |  |  | B
BA-CON-D6-A1-IR-SURVY-0228 | 0 | HYPERLINK | L |  | edge and level for second slab 109.05 cor-cm at A1-03-06 | A1-03-06 | 2025-10-01 | 2025-10-02 |  |  | B
BA-CON-D6-A1-IR-SURVY-0229 | 0 | HYPERLINK | L |  | axis columns for second slab 109.05 cor-cm at A1-03-06 | A1-03-06 | 2025-10-02 | 2025-10-05 |  |  | B
BA-CON-D6-A1-IR-SURVY-0230 | 0 | HYPERLINK | L |  | axis and level for first slab 106.05 cor-cm at A1-06-01 | A1-06-01 | 2025-10-04 | 2025-10-05 |  |  | C | n
BA-CON-D6-A1-IR-SURVY-0230 | 0 | HYPERLINK | L |  | axis and level for first slab 106.05 Duo-cm at A1-06-01 | A1-06-01 | 2025-10-06 | 2025-10-07 |  |  | B | n
BA-CON-D6-A1-IR-SURVY-0231 | 0 | HYPERLINK | L |  | edge and level for second slab 109.05 trio-cm at A1-03-05 | A1-03-05 | 2025-10-04 | 2025-10-05 |  |  | B | n
BA-CON-D6-A1-IR-SURVY-0232 | 0 | HYPERLINK | L |  | edge and level for 3rd slab 112.05 trio-cm at A1-03-03 | A1-03-03 | 2025-10-04 | 2025-10-05 |  |  | B | n
BA-CON-D6-A1-IR-SURVY-0233 | 0 | HYPERLINK | L |  | edge and level for ground slab 103.05 cor-cm at A1-05-05 | A1-05-05 | 2025-10-04 | 2025-10-06 |  |  | B | n
BA-CON-D6-A1-IR-SURVY-0234 | 0 | HYPERLINK | L |  | location and level for rc at A1-04-07 | A1-04-07 | 2025-10-05 | 2025-10-06 |  |  | B | N
BA-CON-D6-A1-IR-SURVY-0235 | 0 | HYPERLINK | L |  | axis and level for Second slab 109.05 Cor-cm at A1-06-06 | A1-06-06 | 2025-10-06 | 2025-10-07 |  |  | B | n
BA-CON-D6-A1-IR-SURVY-0236 | 0 | HYPERLINK | L |  | axis columns for Second slab 109.05 TRIO-CM at A1-03-05 | A1-03-05 | 2025-10-06 |  |  |  |  | n
BA-CON-D6-A1-IR-SURVY-0237 | 0 | HYPERLINK | L |  | axis columns for 3RD slab 112.05 TRIO-CM at A1-03-03 | A1-03-03 | 2025-10-06 | 2025-10-06 |  |  | B | n
BA-CON-D6-A1-IR-SURVY-0238 | 0 | HYPERLINK | L |  | axis and level for 3rd slab trio-c 112.05 at A1-03-01 | A1-03-01 | 2025-10-07 | 2025-10-07 |  |  | B
BA-CON-D6-A1-IR-SURVY-0239 | 0 | HYPERLINK | L |  | axis and level for ground slab trio-D 103.05 at A1-04-02 | A1-04-02 | 2025-10-07 | 2025-10-07 |  |  | B
BA-CON-D6-A1-IR-SURVY-0240 |  | HYPERLINK | L |  | axis columns for ground slab 103.05 cor-cm at A1-05-05 | A1-05-05 | 2025-10-07 | 2025-10-08 |  |  | B
BA-CON-D6-A1-IR-SURVY-0241 |  | HYPERLINK | L |  | axis and level for ground slab 103.05 cor-cm at A1-04-05 | A1-04-05 | 2025-10-08
Formulas:
Status = IF([Return Date]="",IF(TODAY()-[Received Date]>(IF([IR Rev.]=0,S5,S6)),"Overdue","Open"),IF([Return Date]-[Received Date]>(IF([IR Rev.]=0,P5,P6)),"R. with Delay","Replied"))
Status = IF([Return Date]="",IF(TODAY()-'[1](IR)-Survey'!I53>(IF([IR Rev.]=0,S5,S6)),"Overdue","Open"),IF([Return Date]-'[1](IR)-Survey'!I53>(IF([IR Rev.]=0,P5,P6)),"R. with Delay","Replied"))

## (IR)-MEP
Open | 0 | #DIV/0! | 9 - Inspection Request – (IR)CONTECH Log (MEP) A1 | [8 empty] | Project: |  | Badya
Replied | 0 | #DIV/0! | [9 empty] | Contract: |  | 500-004-CC-P8
Overdue | 0 | #DIV/0! | [9 empty] | Contractor: |  | CON.TECH
Reply With Delay | 0 | #DIV/0! | [9 empty] | Consultant: |  | Julius Berger International
Total Actions | 0 | #DIV/0! | [9 empty] | Due Date for Submission Rev. = (0) |  |  |  | 2
Within The Allowed Duration (in overdue field) | [11 empty] | Due Date for Submission Rev.>= (1) |  |  |  | 2
Color of the overdue cell will change to yellow when it remains 1 day only for due date | [11 empty] | Dated on |  | 2025-10-09
Inspection Request No | IR Rev. | IR Latest Rev. | IR Category | Description | Location | Received Date | Due Date | Return Date | Progress | Overdue | Status | Multi Action | Ball In Court | Remarks | Soft (PDF) √ - ꓫ | FileNet
L

## (IR)-FF (hidden)
Open | 0 | 0% | 9 - Inspection Request – (IR) SODIC Log (Fire Fighting) | [8 empty] | Project: |  | Badya
Replied | 0 | 0% | [9 empty] | Contract: |  | 500-004-CC-P8
Overdue | 1 | 100% | [9 empty] | Contractor: |  | CON.TECH
Reply With Delay | 0 | 0% | [9 empty] | Consultant: |  | Julius Berger International
Total Actions | 1 | 100% | [9 empty] | Due Date for Submission Rev. = (0) |  |  |  | 2
Within The Allowed Duration (in overdue field) | [11 empty] | Due Date for Submission Rev.>= (1) |  |  |  | 2
Color of the overdue cell will change to yellow when it remains 1 day only for due date | [11 empty] | Dated on |  | 2025-10-09
Inspection Request No | IR Rev. | IR Latest Rev. | IR Category | Description | Location | Received Date | Due Date | Return Date | Progress | Overdue | Status | Multi Action | Ball In Court | Remarks | Soft (PDF) √ - ꓫ | FileNet
| 0 | - |  |  |  |  | 1900-01-01 |  | 45939 | 45937 | Overdue |  |  |  | √
Formulas:
Due Date = IF([IR Rev.]=0,[Received Date]+Q5,IF([IR Rev.]>=1,[Received Date]+Q6,0))
Progress = IF([Return Date]="",TODAY()-[Received Date],[Return Date]-[Received Date])
Overdue = IF([Due Date]="",0,(IF([Return Date]="",TODAY()-[Due Date],IF([Return Date]-[Due Date]>0,[Return Date]-[Due Date],0))))
Status = IF([Return Date]="",IF(TODAY()-[Received Date]>(IF([IR Rev.]=0,Q5,Q6)),"Overdue","Open"),IF([Return Date]-[Received Date]>(IF([IR Rev.]=0,Q5,Q6)),"R. with Delay","Replied"))

## (IR)-PL (hidden)
Open | 0 | #DIV/0! | 9 - Inspection Request – (IR) SODIC Log (Plumbing) | [8 empty] | Project: |  | Badya
Replied | 0 | #DIV/0! | [9 empty] | Contract: |  | 500-004-CC-P8
Overdue | 0 | #DIV/0! | [9 empty] | Contractor: |  | CON.TECH
Reply With Delay | 0 | #DIV/0! | [9 empty] | Consultant: |  | Julius Berger International
Total Actions | 0 | #DIV/0! | [9 empty] | Due Date for Submission Rev. = (0) |  |  |  | 2
Within The Allowed Duration (in overdue field) | [11 empty] | Due Date for Submission Rev.>= (1) |  |  |  | 2
Color of the overdue cell will change to yellow when it remains 1 day only for due date | [11 empty] | Dated on |  | 2025-10-09
Inspection Request No | IR Rev. | IR Latest Rev. | IR Category | Description | Location | Received Date | Due Date | Return Date | Progress | Overdue | Status | Multi Action | Ball In Court | Remarks | Soft (PDF) √ - ꓫ | FileNet

## (IR)-HVAC (hidden)
Open | 0 | 0% | 9 - Inspection Request – (IR) SODIC Log (HVAC) | [8 empty] | Project: |  | Badya
Replied | 0 | 0% | [9 empty] | Contract: |  | 500-004-CC-P8
Overdue | 1 | 100% | [9 empty] | Contractor: |  | CON.TECH
Reply With Delay | 0 | 0% | [9 empty] | Consultant: |  | Julius Berger International
Total Actions | 1 | 100% | [9 empty] | Due Date for Submission Rev. = (0) |  |  |  | 2
Within The Allowed Duration (in overdue field) | [11 empty] | Due Date for Submission Rev.>= (1) |  |  |  | 2
Color of the overdue cell will change to yellow when it remains 1 day only for due date | [11 empty] | Dated on |  | 2025-10-09
Inspection Request No | IR Rev. | IR Latest Rev. | IR Category | Description | Location | Received Date | Due Date | Return Date | Progress | Overdue | Status | Multi Action | Ball In Court | Remarks | Soft (PDF) √ - ꓫ | FileNet
| 0 | - |  |  |  |  | 1900-01-01 |  | 45939 | 45937 | Overdue |  |  |  | √
Formulas:
Due Date = IF([IR Rev.]=0,[Received Date]+Q5,IF([IR Rev.]>=1,[Received Date]+Q6,0))
Progress = IF([Return Date]="",TODAY()-[Received Date],[Return Date]-[Received Date])
Overdue = IF([Due Date]="",0,(IF([Return Date]="",TODAY()-[Due Date],IF([Return Date]-[Due Date]>0,[Return Date]-[Due Date],0))))
Status = IF([Return Date]="",IF(TODAY()-[Received Date]>(IF([IR Rev.]=0,Q5,Q6)),"Overdue","Open"),IF([Return Date]-[Received Date]>(IF([IR Rev.]=0,Q5,Q6)),"R. with Delay","Replied"))

## (IR)-Elect.
Open | 0 | #DIV/0! | 9 - Inspection Request – (IR) CONTECH Log (Electrical) | [8 empty] | Project: |  | Badya
Replied | 0 | #DIV/0! | [9 empty] | Contract: |  | 500-004-CC-P8
Overdue | 0 | #DIV/0! | [9 empty] | Contractor: |  | CON.TECH
Reply With Delay | 0 | #DIV/0! | [9 empty] | Consultant: |  | Julius Berger International
Total Actions | 0 | #DIV/0! | [9 empty] | Due Date for Submission Rev. = (0) |  |  |  | 2
Within The Allowed Duration (in overdue field) | [11 empty] | Due Date for Submission Rev.>= (1) |  |  |  | 2
Color of the overdue cell will change to yellow when it remains 1 day only for due date | [11 empty] | Dated on |  | 2025-10-09
Inspection Request No | IR Rev. | IR Latest Rev. | HYPWRLINK | Description | Location | Received Date | Due Date | Status | Multi Action | Overdue | Return Date |  | Ball In Court | Remarks | Soft (PDF) √ - ꓫ | FileNet
BADYA-CON-A1-IR-ELEC-0001 | 0 | L | ELEC | power, low current, Lighting System Ground floor TRIO C A1-03-07 | A1-03-07 | 2025-06-16 | 2025-07-08 | R. with Delay | B
BADYA-CON-A1-IR-ELEC-0002 | 0 | L | HYPWRLINK | power, low current, Lighting System Ground floor TRIO CM A1-03-03 | A1-03-03 | 2025-06-17 | 2025-07-08 | R. with Delay | B
BADYA-CON-A1-IR-ELEC-0003 | 0 | L | HYPWRLINK | power, low current, Lighting System Ground floor TRIO CM A1-03-05 | A1-03-05 | 2025-06-18 | 2025-07-08 | R. with Delay | B
BADYA-CON-A1-IR-ELEC-0004 | 0 | L | HYPWRLINK | power, low current, Lighting System Ground floor TRIO C A1-03-01 | A1-03-01 | 2025-06-23 | 2025-07-08 | R. with Delay | B
BADYA-CON-A1-IR-ELEC-0005 | 0 | L | HYPWRLINK | power, low current, Lighting System Ground floor TRIO CM A1-03-02 | A1-03-02 | 2025-06-29 | 2025-07-08 | R. with Delay | B
BADYA-CON-A1-IR-ELEC-0006 | 0 | L | HYPWRLINK | power, low current, Lighting System Ground floor COR CM A1-03-06 | A1-03-06 | 2025-06-29 | 2025-07-08 | R. with Delay | B
BADYA-CON-A1-IR-ELEC-0007 | 0 | L | HYPWRLINK | power, low current, Lighting System Ground floor COR C A1-03-04 | A1-03-04 | 2025-07-01 | 2025-07-08 | R. with Delay | B
BADYA-CON-A1-IR-ELEC-0008 | 0 | L | HYPWRLINK | power, low current, Lighting System 1ST floor TRIO C A1-03-07 | A1-03-07 | 2025-07-01 | 2025-07-15 | R. with Delay | B
BADYA-CON-A1-IR-ELEC-0009 | 0 | L | HYPWRLINK | power, low current, Lighting System 1ST floor TRIO C A1-03-03 | A1-03-03 | 2025-07-16 | 2025-07-21 | R. with Delay | B
BADYA-CON-A1-IR-ELEC-0010 | 0 | L | HYPWRLINK | power, low current, Lighting System 1ST floor TRIO C A1-03-05 | A1-03-05 | 2025-07-16 | 2025-07-21 | R. with Delay | B
BADYA-CON-A1-IR-ELEC-0011 | 0 | L | HYPWRLINK | power, low current, Lighting System GROUND floor TRIO D A1-05-06 | A1-05-06 | 2025-07-17 | 2025-07-28 | R. with Delay | B
BADYA-CON-A1-IR-ELEC-0012 | 0 | L | HYPWRLINK | power, low current, Lighting System FIRST floor TRIO C A1-03-01 | A1-03-01 | 2025-07-17 | 2025-07-28 | R. with Delay | B | B
BADYA-CON-A1-IR-ELEC-0013 | 0 | L | HYPWRLINK | power, low current, Lighting System GROUND floor TRIO D A1-05-07 | A1-05-07 | 2025-07-27 | 2025-07-29 | Replied | B
BADYA-CON-A1-IR-ELEC-0014 | 0 | L | HYPWRLINK | power, low current, Lighting System 1st floor COR CM A1-03-06 | A1-03-06 | 2025-07-27 | 2025-07-30 | R. with Delay | B
BADYA-CON-A1-IR-ELEC-0015 | 0 | L | HYPWRLINK | power, low current, Lighting System first floor TRIO CM A1-03-02 | A1-03-02 | 2025-07-30 | 2025-08-04 | R. with Delay | B
BADYA-CON-A1-IR-ELEC-0016 | 0 | L | HYPWRLINK | power, low current, Lighting System GROUND floor COR-C A1-05-02 | A1-05-02 | 2025-08-03 | 2025-08-24 | R. with Delay | B
BADYA-CON-A1-IR-ELEC-0017 | 0 | L | HYPWRLINK | power, low current, Lighting System 1st floor COR-C A1-03-04 | A1-03-04 | 2025-08-03 | 2025-08-06 | R. with Delay | B
BADYA-CON-A1-IR-ELEC-0018 | 0 | L | HYPWRLINK | power, low current, Lighting System GROUND floor COR CM A1-06-06 | A1-06-06 | 2025-08-06 | 2025-08-10 | R. with Delay | B
BADYA-CON-A1-IR-ELEC-0019 | 0 | L | HYPWRLINK | power, low current, Lighting System GROUND floor TRIO DM A1-06-03 | A1-06-03 | 2025-08-06 | 2025-08-17 | R. with Delay | B
BADYA-CON-A1-IR-ELEC-0020 | 0 | L | HYPWRLINK | power, low current, Lighting System GROUND floor DUO CM A1-06-02 | A1-06-02 | 2025-08-09 | 2025-08-13 | R. with Delay | B
BADYA-CON-A1-IR-ELEC-0021 | 0 | L | HYPWRLINK | power, low current, Lighting System GROUND floor TRIO DM A1-05-01 | A1-05-01 | 2025-08-13 | 2025-08-20 | R. with Delay | B
BADYA-CON-A1-IR-ELEC-0022 | 0 | L | HYPWRLINK | power, low current, Lighting System GROUND floor COR C A1-06-04 | A1-06-04 | 2025-08-13 | 2025-08-20 | R. with Delay | B
BADYA-CON-A1-IR-ELEC-0023 | 0 | L | HYPWRLINK | power, low current, Lighting System 2nd floor TRIO C A1-03-07 | A1-03-07 | 2025-08-18 | 2025-08-24 | R. with Delay | B
BADYA-CON-A1-IR-ELEC-0024 | 0 | L | HYPWRLINK | power, low current, Lighting System GROUND floor TRIO D A1-05-03 | A1-05-03 | 2025-08-20 | 2025-08-24 | R. with Delay | B
BADYA-CON-A1-IR-ELEC-0025 | 0 | L | HYPWRLINK | power, low current, Lighting System GROUND floor DUO CM A1-06-01 | A1-06-01 | 2025-08-21 | 2025-08-25 | R. with Delay | B
BADYA-CON-A1-IR-ELEC-0026 | 0 | L | HYPWRLINK | power, low current, Lighting System 2nd floor TRIO C A1-03-03 | A1-03-03 | 2025-08-24 | 2025-08-26 | Replied | B
BADYA-CON-A1-IR-ELEC-0027 | 0 | L | HYPWRLINK | power, low current, Lighting System GROUND floor TRIO DM A1-06-05 | A1-06-05 | 2025-08-25 | 2025-09-01 | R. with Delay | B
BADYA-CON-A1-IR-ELEC-0028 | 0 | L | HYPWRLINK | power, low current, Lighting System 2nd floor COR-C A1-03-04 | A1-03-04 | 2025-08-27 | 2025-09-02 | R. with Delay | B
BADYA-CON-A1-IR-ELEC-0029 | 0 | L | HYPWRLINK | power , low current ,Lighting System 2nd floor TRIO CM A1-03-02 | A1-03-02 | 2025-09-06 | 2025-09-10 | R. with Delay | B
BADYA-CON-A1-IR-ELEC-0030 | 0 | L | HYPWRLINK | power , low current ,Lighting System 1st floor TRIO DM A1-06-05 | A1-06-05 | 2025-09-07 | 2025-09-21 |  | C
BADYA-CON-A1-IR-ELEC-0031 | 0 | L | HYPWRLINK | power , low current ,Lighting System 1st floor TRIO D A1-05-06 | A1-05-06 | 2025-09-09 | 2025-09-13 |  | B
BADYA-CON-A1-IR-ELEC-0032 | 0 | L | HYPWRLINK | power , low current ,Lighting System 2nd floor TRIO C A1-03-01 | A1-03-01 | 2025-09-10 | 2025-09-16 |  | B
BADYA-CON-A1-IR-ELEC-0033 | 0 | L | HYPWRLINK | power , low current ,Lighting System 1st floor TRIO DM A1-05-01 | A1-05-01 | 2025-09-11 | 2025-09-16 |  | B
BADYA-CON-A1-IR-ELEC-0034 | 0 | L | HYPWRLINK | power , low current ,Lighting System ground floor TRIO DM A1-05-04 | A1-05-04 | 2025-09-11 | 2025-09-16 |  | B
BADYA-CON-A1-IR-ELEC-0035 | 0 | L | HYPWRLINK | power, low current, Lighting System 1st floor TRIO-DM A1-06-03 | A1-06-03 | 2025-09-15 | 2025-10-07 |  | B
BADYA-CON-A1-IR-ELEC-0036 | 0 | L | HYPWRLINK | power, low current, Lighting System 1ST floor COR-CM A1-06-06 | A1-06-06 | 2025-09-15 | 2025-09-18 |  | B
BADYA-CON-A1-IR-ELEC-0037 | 0 | L | HYPWRLINK | power , low current ,Lighting System 1st floor TRIO-D A1-05-07 | A1-05-07 | 2025-09-20 | 2025-09-25 |  | B
BADYA-CON-A1-IR-ELEC-0038 | 0 | L | HYPWRLINK | power , low current ,Lighting System 1st floor COR-C A1-05-02 | A1-05-02 | 2025-09-24 | 2025-09-30 |  | B |  | H
BADYA-CON-A1-IR-ELEC-0039 | 0 | L | HYPWRLINK | power , low current ,Lighting System 1st floor COR-C A1-06-04 | A1-06-04 | 2025-09-24 | 2025-10-07 |  | D
BADYA-CON-A1-IR-ELEC-0040 | 0 | L | HYPWRLINK | power , low current ,Lighting System 3rd floor TRIO-C A1-03-07 | A1-03-07 | 2025-09-24 | 2025-09-30 |  | B |  | H
BADYA-CON-A1-IR-ELEC-0041 | 0 | L | HYPWRLINK | power , low current ,Lighting System 2nd floor COR CM A1-03-06 | A1-03-06 | 2025-09-27 | 2025-10-02 |  | B
BADYA-CON-A1-IR-ELEC-0042 | 1 | L | HYPWRLINK | power , low current ,Lighting System 2nd floor TRIO-CM A1-03-05 | A1-03-05 | 2025-09-29
BADYA-CON-A1-IR-ELEC-0043 | 2 | L | HYPWRLINK | power , low current ,Lighting System GROUND floor COR-CM A1-05-05 | A1-05-05 | 2025-09-29 | 2025-10-02 |  | B
BADYA-CON-A1-IR-ELEC-0044 | 0 | L | HYPWRLINK | power , low current ,Lighting System 3rd floor TRIO-CM-A1-03-03 | A1-03-03 | 2025-10-04
BADYA-CON-A1-IR-ELEC-0045 | 0 | L | HYPWRLINK | power , low current ,Lighting System 1st floor DUO-C A1-06-02 | A1-06-02 | 2025-10-08
BADYA-CON-A1-IR-ELEC-0046 | 0 | L | HYPWRLINK | power , low current ,Lighting System GROUND floor COR-CM-A1-04-03 | A1-04-03 | 2025-10-09
Formulas:
Status = IF([Due Date]="",IF(TODAY()-[Received Date]>(IF([IR Rev.]=0,R5,R6)),"Overdue","Open"),IF([Due Date]-[Received Date]>(IF([IR Rev.]=0,Q5,Q6)),"R. with Delay","Replied"))

## (IR)-Infra (hidden)
Open | 0 | 0% | 9 - Inspection Request – (IR) SODIC Log (Infrastructure) | [8 empty] | Project: |  | Badya
Replied | 0 | 0% | [9 empty] | Contract: |  | 500-004-CC-P8
Overdue | 1 | 100% | [9 empty] | Contractor: |  | CON.TECH
Reply With Delay | 0 | 0% | [9 empty] | Consultant: |  | Julius Berger International
Total Actions | 1 | 100% | [9 empty] | Due Date for Submission Rev. = (0) |  |  |  | 2
Within The Allowed Duration (in overdue field) | [11 empty] | Due Date for Submission Rev.>= (1) |  |  |  | 2
Color of the overdue cell will change to yellow when it remains 1 day only for due date | [11 empty] | Dated on |  | 2025-10-09
Inspection Request No | IR Rev. | IR Latest Rev. | IR Category | Description | Location | Received Date | Due Date | Return Date | Progress | Overdue | Status | Multi Action | Ball In Court | Remarks | Soft (PDF) √ - ꓫ | FileNet
| 0 | - |  |  |  |  | 1900-01-01 |  | 45939 | 45937 | Overdue |  |  |  | √
Formulas:
Due Date = IF([IR Rev.]=0,[Received Date]+Q5,IF([IR Rev.]>=1,[Received Date]+Q6,0))
Progress = IF([Return Date]="",TODAY()-[Received Date],[Return Date]-[Received Date])
Overdue = IF([Due Date]="",0,(IF([Return Date]="",TODAY()-[Due Date],IF([Return Date]-[Due Date]>0,[Return Date]-[Due Date],0))))
Status = IF([Return Date]="",IF(TODAY()-[Received Date]>(IF([IR Rev.]=0,Q5,Q6)),"Overdue","Open"),IF([Return Date]-[Received Date]>(IF([IR Rev.]=0,Q5,Q6)),"R. with Delay","Replied"))

## (IR)-Mob (hidden)
Open | 0 | 0% | 9 - Inspection Request – (IR) SODIC Log (Moblization) | [8 empty] | Project: |  | Badya
Replied | 0 | 0% | [9 empty] | Contract: |  | 500-004-CC-P8
Overdue | 1 | 100% | [9 empty] | Contractor: |  | CON.TECH
Reply With Delay | 0 | 0% | [9 empty] | Consultant: |  | Julius Berger International
Total Actions | 1 | 100% | [9 empty] | Due Date for Submission Rev. = (0) |  |  |  | 2
Within The Allowed Duration (in overdue field) | [11 empty] | Due Date for Submission Rev.>= (1) |  |  |  | 2
Color of the overdue cell will change to yellow when it remains 1 day only for due date | [11 empty] | Dated on |  | 2025-10-09
Inspection Request No | IR Rev. | IR Latest Rev. | IR Category | Description | Location | Received Date | Due Date | Return Date | Progress | Overdue | Status | Multi Action | Ball In Court | Remarks | Soft (PDF) √ - ꓫ | FileNet
| 0 | - |  |  |  |  | 1900-01-01 |  | 45939 | 45937 | Overdue |  |  |  | √
Formulas:
Due Date = IF([IR Rev.]=0,[Received Date]+Q5,IF([IR Rev.]>=1,[Received Date]+Q6,0))
Progress = IF([Return Date]="",TODAY()-[Received Date],[Return Date]-[Received Date])
Overdue = IF([Due Date]="",0,(IF([Return Date]="",TODAY()-[Due Date],IF([Return Date]-[Due Date]>0,[Return Date]-[Due Date],0))))
Status = IF([Return Date]="",IF(TODAY()-[Received Date]>(IF([IR Rev.]=0,Q5,Q6)),"Overdue","Open"),IF([Return Date]-[Received Date]>(IF([IR Rev.]=0,Q5,Q6)),"R. with Delay","Replied"))

## (IR)-LS (hidden)
Open | 0 | 0% | 9 - Inspection Request – (IR) SODIC Log (Landscape) | [8 empty] | Project:
Replied | 0 | 0% | [9 empty] | Contract:
Overdue | 1 | 100% | [9 empty] | Contractor:
Reply With Delay | 0 | 0% | [9 empty] | Consultant:
Total Actions | 1 | 100% | [9 empty] | Due Date for Submission Rev. = (0) |  |  |  | 2
Within The Allowed Duration (in overdue field) | [11 empty] | Due Date for Submission Rev.>= (1) |  |  |  | 2
Color of the overdue cell will change to yellow when it remains 1 day only for due date | [11 empty] | Dated on |  | 2025-10-09
Inspection Request No | IR Rev. | IR Latest Rev. | IR Category | Description | Location | Received Date | Due Date | Return Date | Progress | Overdue | Status | Multi Action | Ball In Court | Remarks | Soft (PDF) √ - ꓫ | FileNet
| 0 | - |  |  |  |  | 1900-01-01 |  | 45939 | 45937 | Overdue |  |  |  | √
Formulas:
Due Date = IF([IR Rev.]=0,[Received Date]+Q5,IF([IR Rev.]>=1,[Received Date]+Q6,0))
Progress = IF([Return Date]="",TODAY()-[Received Date],[Return Date]-[Received Date])
Overdue = IF([Due Date]="",0,(IF([Return Date]="",TODAY()-[Due Date],IF([Return Date]-[Due Date]>0,[Return Date]-[Due Date],0))))
Status = IF([Return Date]="",IF(TODAY()-[Received Date]>(IF([IR Rev.]=0,Q5,Q6)),"Overdue","Open"),IF([Return Date]-[Received Date]>(IF([IR Rev.]=0,Q5,Q6)),"R. with Delay","Replied"))

## (IR)-Safety (hidden)
Open | 0 | 0% | 9 - Inspection Request – (IR) SODIC Log (Safety) | [8 empty] | Project:
Replied | 0 | 0% | [9 empty] | Contract:
Overdue | 1 | 100% | [9 empty] | Contractor:
Reply With Delay | 0 | 0% | [9 empty] | Consultant:
Total Actions | 1 | 100% | [9 empty] | Due Date for Submission Rev. = (0) |  |  |  | 2
Within The Allowed Duration (in overdue field) | [11 empty] | Due Date for Submission Rev.>= (1) |  |  |  | 2
Color of the overdue cell will change to yellow when it remains 1 day only for due date | [11 empty] | Dated on |  | 2025-10-09
Inspection Request No | IR Rev. | IR Latest Rev. | IR Category | Description | Location | Received Date | Due Date | Return Date | Progress | Overdue | Status | Multi Action | Ball In Court | Remarks | Soft (PDF) √ - ꓫ | FileNet
| 0 | - |  |  |  |  | 1900-01-01 |  | 45939 | 45937 | Overdue |  |  |  | √
Formulas:
Due Date = IF([IR Rev.]=0,[Received Date]+Q5,IF([IR Rev.]>=1,[Received Date]+Q6,0))
Progress = IF([Return Date]="",TODAY()-[Received Date],[Return Date]-[Received Date])
Overdue = IF([Due Date]="",0,(IF([Return Date]="",TODAY()-[Due Date],IF([Return Date]-[Due Date]>0,[Return Date]-[Due Date],0))))
Status = IF([Return Date]="",IF(TODAY()-[Received Date]>(IF([IR Rev.]=0,Q5,Q6)),"Overdue","Open"),IF([Return Date]-[Received Date]>(IF([IR Rev.]=0,Q5,Q6)),"R. with Delay","Replied"))

## (IR)-Elev. (hidden)
Open | 0 | 0% | 9 - Inspection Request – (IR) SODIC Log (Elevators) | [8 empty] | Project:
Replied | 0 | 0% | [9 empty] | Contract:
Overdue | 1 | 100% | [9 empty] | Contractor:
Reply With Delay | 0 | 0% | [9 empty] | Consultant:
Total Actions | 1 | 100% | [9 empty] | Due Date for Submission Rev. = (0) |  |  |  | 2
Within The Allowed Duration (in overdue field) | [11 empty] | Due Date for Submission Rev.>= (1) |  |  |  | 2
Color of the overdue cell will change to yellow when it remains 1 day only for due date | [11 empty] | Dated on |  | 2025-10-09
Inspection Request No | IR Rev. | IR Latest Rev. | IR Category | Description | Location | Received Date | Due Date | Return Date | Progress | Overdue | Status | Multi Action | Ball In Court | Remarks | Soft (PDF) √ - ꓫ | FileNet
| 0 | - |  |  |  |  | 1900-01-01 |  | 45939 | 45937 | Overdue |  |  |  | √
Formulas:
Due Date = IF([IR Rev.]=0,[Received Date]+Q5,IF([IR Rev.]>=1,[Received Date]+Q6,0))
Progress = IF([Return Date]="",TODAY()-[Received Date],[Return Date]-[Received Date])
Overdue = IF([Due Date]="",0,(IF([Return Date]="",TODAY()-[Due Date],IF([Return Date]-[Due Date]>0,[Return Date]-[Due Date],0))))
Status = IF([Return Date]="",IF(TODAY()-[Received Date]>(IF([IR Rev.]=0,Q5,Q6)),"Overdue","Open"),IF([Return Date]-[Received Date]>(IF([IR Rev.]=0,Q5,Q6)),"R. with Delay","Replied"))

## (IR)-General (hidden)
Open | 0 | 0% | 9 - Inspection Request – (IR) SODIC Log (General) | [8 empty] | Project:
Replied | 0 | 0% | [9 empty] | Contract:
Overdue | 1 | 100% | [9 empty] | Contractor:
Reply With Delay | 0 | 0% | [9 empty] | Consultant:
Total Actions | 1 | 100% | [9 empty] | Due Date for Submission Rev. = (0) |  |  |  | 2
Within The Allowed Duration (in overdue field) | [11 empty] | Due Date for Submission Rev.>= (1) |  |  |  | 2
Color of the overdue cell will change to yellow when it remains 1 day only for due date | [11 empty] | Dated on |  | 2025-10-09
Inspection Request No | IR Rev. | IR Latest Rev. | IR Category | Description | Location | Received Date | Due Date | Return Date | Progress | Overdue | Status | Multi Action | Ball In Court | Remarks | Soft (PDF) √ - ꓫ | FileNet
| 0 | - |  |  |  |  | 1900-01-01 |  | 45939 | 45937 | Overdue |  |  |  | √
Formulas:
Due Date = IF([IR Rev.]=0,[Received Date]+Q5,IF([IR Rev.]>=1,[Received Date]+Q6,0))
Progress = IF([Return Date]="",TODAY()-[Received Date],[Return Date]-[Received Date])
Overdue = IF([Due Date]="",0,(IF([Return Date]="",TODAY()-[Due Date],IF([Return Date]-[Due Date]>0,[Return Date]-[Due Date],0))))
Status = IF([Return Date]="",IF(TODAY()-[Received Date]>(IF([IR Rev.]=0,Q5,Q6)),"Overdue","Open"),IF([Return Date]-[Received Date]>(IF([IR Rev.]=0,Q5,Q6)),"R. with Delay","Replied"))